## Pgm Tracker Overview
Berinsfield Garden Village Programme Tracker South Oxfordshire District Council June 2025
Berinsfield Community Delivery Plan
Project Number | SODC Corporate Priorities | Project Name | Status | Priority | Description | Lead Organisation | SODC BGV - Budget allocation | SODC BGV - Committed/Spent | SODC BGV - Balance | Funding Type | Bi-monthly Update | Monthly Update | Monthly Update | Monthly Update | Monthly Update |  |  | Monthly Update | Monthly Update | Monthly Update | Monthly Update | Monthly Update | Monthly Update | Monthly Update | Monthly Update | Monthly Update | Monthly Update | Monthly Update
Housing and The Built Environement | [11 empty] | January 2024 Update | February Update | March Update | April Update | May Update | June Update | July 2024 Update | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-05-25 | 2025-06-25 | 2025-07-25 | 2025-08-25 | 2025-09-25 | 2025-10-25 | 2025-11-25 | 2025-12-25 | 2026-01-25 | 2026-02-25
1 | Homes and infrastructure that meet local needs | Land and development agreement | In progress | H | Continue negotiations and agreement with land owner and agent on the development and principles of the new Garden Village Development following the masterplanning exercise | SODC - Place | 0 | 0 | 0 | SODC - BGV | Disccusions will continue through the planning application process. | Disccusions will continue through the planning application process. | Disccusions will continue through the planning application process. | Disccusions will continue through the planning application process. | Disccusions will continue through the planning application process. |  | Discussions will continue through the planning application process. | Discussions will continue through the planning application process. | 2024-08-01: Discussions will continue through the planning application process. Engagement from SODC Property Team iniatiated to discuss access of Land at Fane Drive.; 2024-09-01: Discussions will continue through the planning application process. Engagement from SODC Property Team iniatiated to discuss access of Land at Fane Drive. A delivery agreement is currently being drafted by Ptarmgian. An initial draft was shared with SODC for review and comment.; 2024-10-01: Discussions will continue through the planning application process. Engagement from SODC Property Team iniatiated to discuss access of Land at Fane Drive. A delivery agreement is currently being drafted by Ptarmgian. An initial draft was shared with SODC for review and comment.; 2024-12-01: Discussions continue on a regular basis. More regular engagement by Ptarmigan with SODC Property Team required to discuss and progress access arrangements off Land at Fane Drive. A delivery agreement has been drafted by Ptarmigan. SODC has fed back comments.; 2025-01-01: A delivery agreement has been drafted by Ptarmigan. SODC has fed back comments; 2025-02-01: A delivery agreement has been drafted by Ptarmigan. SODC has fed back comments; 2025-03-01: A delivery agreement has been drafted by Ptarmigan. SODC has fed back comments.; 2025-05-25: A delivery agreement has been drafted by Ptarmigan. SODC has fed back comments.; 2025-06-25: A delivery agreement has been drafted by Ptarmigan. SODC has fed back comments.
2 | Homes and infrastructure that meet local needs | Community-led Masterplanning Exercise | In progress | H | Arrange and hold masterplanning exercises with the community, Parish Council and other key stakeholders to seek options, ideas and views to inform a comprehensive masterplan for the Garden Village, working with the landowner of the STRAT 10i adjacent land. This will allow stakeholder buy-in to a development that positively enhances the local amenity and delivers on the aspirations of the local community. | Ptarmingan (JTP) | 0 | 0 | 0 | N/A | First working draft Masterplan Framework Document currently live. Pre Planning Application meetings scheduled week commencing 5 December. Feedback summary from the Landscape and Movement stakeholders workshop complete. Ptarmigan are arranging to undertake a next phase of engagement that includes a workshop with Parish Councilllors and a community hub and stewardship / governance workshop, followed by a Masterplan Exhibition in January 2024. | The Berinsfield Masterplan Framework Document will be launched at a public exhibition on Tuesday 23 January 2024. Pre planning application (PPA) discussions continue with the local planning authrority. | Pre-planning application discussions continue. NW to set up more detail conversation with afforable housing. | Internal direction agreed to help bring together our wants on the S106 ask on the regeneration is outlined. Building an evidence based regeneration package to inform the S106. To unlock the viability of the Garden Village to be delivered on Land at Mount Farm, which is undpinned by the green belt being released for development for exceptional circumstances of regeneration to meet local need. Key elements of defining the regeneration package include: Sports, Leisure and Recreation Community Infrastructure (i.e. Community Hub) Health Community Energy Community Development Education, Skills and Employment Affordable Housing Design and Implementation Phasing and Accelarated Delivery Stewardship and Management Team to start coordinating evidence to inform discussions. NW to circulate. Floodiong issues should be picked up, any alievation schemes - Environment heading? ACTION: What is possible on our own land for floodign alievation? what is possible to influence other agencis to look at the problem of flooding in the issues. Bring together landowners to investigate issue? | NW/AD currently pulling together data on SODC wants for the regenration package. It is likely that the Community Hub in existing Berinsfield will feature. Internal focus groups to advance these discussions will be scheduled. Angela to add information ragarding Housing Needs Assessment refresh work. xxxxxxxxxxxxxxxxxxxxxxxxxxxxx | Housing Needs Assessment (HNA) quote received from qualified potential bidder and will be assessed w/c 13 May. If bid accepted a contract will be put into place within the following few days. The specification and bid look at housing needs including afiordable housing with both 40% and 50% level within any new developmnent. | Discussions continue between SODC and Ptarmigan to inform the regeneration package and S106 agreement. It is important that we build an evidence based regeneration package to inform the S106 to unlock the viability of the Garden Village to be delivered on Land at Mount Farm. This is underpinned by the green belt being released for development for exceptional circumstances of regeneration to meet local need.Housing Needs Assessment (HNA) contract agreed with sucessful bidder and initiation meeting held on 20 June. The specification and bid look at housing needs including affordable housing with both 40% and 50% level within any new developmnent. Draft report expected in August 24 and fuill report in September 24. A household survey to inform the HNA is expected to be disptatched to households by 10 July with doorstep collection by field operatives by end of July. | Discussions continue between SODC and Ptarmigan to inform the regeneration package and S106 agreement. It is important that we build an evidence based regeneration package to inform the S106 to unlock the viability of the Garden Village to be delivered on Land at Mount Farm. This is underpinned by the green belt being released for development for exceptional circumstances of regeneration to meet local need.Housing Needs Assessment (HNA) contract agreed with sucessful bidder and initiation meeting held on 20 June. The specification and bid look at housing needs including affordable housing with both 40% and 50% level within any new developmnent. Draft report expected in August 24 and fuill report in September 24. A household survey to inform the HNA is expected to be disptatched to households by 10 July with doorstep collection by field operatives by end of July. | 2024-08-01: August Update; 2024-09-01: Discussions continue between SODC and Ptarmigan to inform the regeneration package and S106 agreement. The team met with Ptarmigan Land to review initial drafts that outline the S106 and added value of the regeneration package. This was reviewed against viability calculations considering various scenarios with housing delivery. Discussions will continue to refine the approach. The BGV team are currently drafting a Berinsfield Regeneration Strategy which will be considered by South cabinet in March 2025. The strategy will outline the difference between the S106 statutory ask and the regeneration request. It is important that we build an evidence based regeneration package to inform the S106 to unlock the viability of the Garden Village to be delivered on Land at Mount Farm. This is underpinned by the green belt being released for development for exceptional circumstances of regeneration to meet local need.; 2024-10-01: The BGV team are currently drafting a Berinsfield Regeneration Strategy which will be considered by South cabinet in March 2025. The strategy will outline the difference between the S106 statutory ask and the regeneration request. Currently working with specialist teams including affordable housing, climate and economic development to draft chapters of the document. Aiming for public consultation in January 2025. It is important that we build an evidence based regeneration package to inform the S106 to unlock the viability of the Garden Village to be delivered on Land at Mount Farm. This is underpinned by the green belt being released for development for exceptional circumstances of regeneration to meet local need.; 2024-12-01: The BGV team are currently drafting a Berinsfield Regeneration Strategy which will be considered by South cabinet in March 2025. The strategy will outline the difference between the S106 statutory ask and the regeneration request from any development that may come forward on Land at Mount Farm Berinsfield. A public consultation on the themes and items suggested to support regeneration of the existing village will be launched on 8 January 2025. The consultation will be open for a month and other in person opportunities for engagement will be held towards the end of January. Gathering public feedback will support us in understanding residents priorities or any gaps in proposals. It is important that we build an evidence based regeneration package to inform the S106 to inform viability and delivery of the Garden Village on Land at Mount Farm. This is underpinned by the Green Belt being released for development for exceptional circumstances of regeneration to meet local need.; 2025-01-01: The online survey was launched on Thursday 9 January, along side two drop in session held at St Mary and St Berin Church on 2 and 4 February. Our Community Development Officer also completed extensive enagement on the ground speaking to residents over the course of two weeks. Next steps will be to anaylise the feedback, refine the strategy ahead of taking it through to cabinet on 10 April.; 2025-02-01: Following the public consultation, the team is currently analysing feedback collected to help refine the strategy document. • Around 110 survey forms were received, in addition to anecdotal conversations captured through engagement completed by our Community Development Officer on the ground. • The timeline to take this through our own internal decision-making process is now pushed back by one month. This is to allow more time required to work on the strategy in partnership with OCC and to accommodate the outcome of the JLP process as it unfolds. We will also reengage with the Parish Council on its progress. • It is likely to be considered by SODC at the Cabinet meeting scheduled in May.; 2025-03-01: Following the public consultation, the team is currently analysing feedback collected to help refine the strategy document. • 110 survey responses were received (102 surveys and 8 alternative submissions), in addition to anecdotal conversations captured through engagement completed by our Community Development Officer on the ground. • The timeline to take this through our own internal decision-making process is now pushed back slightly. This is to allow more time required to work on the strategy in partnership with OCC and to accommodate the outcome of the JLP process as it unfolds. We will also re-engage with the Parish Council on its progress. • It is likely to be considered by SODC at the Cabinet meeting scheduled in June.; 2025-05-25: The timeline to take this through our own internal decision-making process is now pushed back. This is to allow more time required to work on the strategy in partnership with OCC and to accommodate the outcome of the JLP process as it unfolds. Re-enagement engage with the Parish Council on its progress. The strategy and paper will be considered by South Cabinet in October.; 2025-06-25: The timeline to take the Regeneration Strategy through SODC's internal decision-making process is now pushed back. This is to allow more time required to work on the strategy in partnership with OCC and to accommodate the outcome of the JLP process as it unfolds. The strategy and paper will be considered by South Cabinet in October, alongside a refocused Community Delivery Plan.
3 | Homes and infrastructure that meet local needs | Community Facilities | In progress | H | Commission feasibility studies to inform a business case on full redevelopment or refurbishment of community and sports facilities (condition, design, specification, cost and management models). This will develop and advance options and ideas for the design of a community wellbeing hub and consider opportunities to co-locate several existing organisations and facilities. Development of the project will be completed in consultation with local partners and service delivery. | SODC - BGV/Place | 55373 | 52373 | 3000 | SODC - BGV | The Community Hub Feasibility Study is complete. Ptarmigan will now take forward the next stages of the community hub work as part of the masterplanning process. | Project complete. | Project complete. | Project complete. | Project complete - this is likely to inform the regeneration package. |  | The Community Hub Feasibility Study is complete. Ptarmigan will now take forward the next stages of the community hub work as part of the masterplanning process. It may be considered that the Community Hub is integral to the regeneraiton package for the existing village. |  | 2024-08-01: August Update; 2024-09-01: The Community Hub Feasibility Study is complete. Ptarmigan will now take forward the next stages of the community hub work as part of the masterplanning process. It may be considered that the Community Hub is integral to the regeneration package for the existing village. See further project development for Abbey Leisure Centre in project 5.; 2024-10-01: The Community Hub Feasibility Study is complete. Ptarmigan will now take forward the next stages of the community hub work as part of the masterplanning. It may be considered that the Community Hub is integral to the regeneration package for the existing village. See further project development for Abbey Leisure Centre in project 5. process.; 2024-12-01: A procurement exercise was undertaken to obtain further architectural and cost analysis services to develop the Community Facilities (Stage 1) recommendations and further feasibility options. This includes taking on board possible future leisure needs requirements such as expanding the swimming pool at Abbey Sports Centre.; 2025-01-01: A first draft of the architectural and cost analysis report to develop the Community Facilities (Stage 1) recommendations and further feasibility options is received. The team are currently reviewing recommendations and outcomes within the report.; 2025-02-01: The architectural and cost analysis report to develop the Community Facilities (Stage 1) recommendations and further feasibility options is complete. Cost anaylsis has helped inform the regeneration work.; 2025-03-01: The architectural and cost analysis report to develop the Community Facilities (Stage 1) recommendations and further feasibility options is complete. Cost analysis has helped inform the regeneration work.; 2025-05-25: The architectural and cost analysis report to develop the Community Facilities (Stage 1) recommendations and further feasibility options is complete. Cost analysis has helped inform the regeneration work.; 2025-06-25: The architectural and cost analysis report to develop the Community Facilities (Stage 1) recommendations and further feasibility options is complete. Cost analysis has helped inform the regeneration work.
4 | Homes and infrastructure that meet local needs | Stewardship | Delayed | H | Commission a study into the sustainable management of community facilities and a creation of an outline financial model to adopt an effective long-term management stewardship model to maintain the quality of the whole Garden Village, having regard to the discrete management model for the community facilities if these are delivered prior to a comprehensive masterplan. | SODC - BGV/Place | 10000 | 0 | 10000 | SODC - BGV | First consideration of a stewardship model and governance structure was considered as part of the Community Hub Feasibility Study. Within this it is considered how to scale up any model to cater for potential growth in the future. Proposals included a suggested charitable Management Trust, Berinsfield Community Management Trust (BCMT), sitting alongside and working closely with the Parish Council, with full stakeholder and user group participation, which was recommended as the best model. This recommendation will need to be considered further by relevant stakeholders and refined in order to fully address the considerations. In particular, individual voluntary and community organisations participating in these proposals for new community facilities will themselves have existing governance and management arrangements which will need to continue, evolve or be merged into this proposed new structure. It is usually helpful to establish a governance working group made up of all interested stakeholders to consider a new proposed governance framework. A Chair person will be required to coordinate and facilitate the discussions and given that there may be some negotiations as part of this process, it may be helpful to have an independent Chair to enable all parties to fully participate without any conflicts of interest. | Stewardship to be considered through the masterplanning process and PPA discussions on how assetts will be managed in the future. It is likely to consider the first thoughts on stewardship models and governance outlined in the Community Hub Feasibility Study. | Ptarmigan have engage with Mark Pratchett regarding early discussion on Stewardship. | Ptarmigan have engage with Mark Pratchett regarding early discussion on Stewardship. Stewardship also to be consider as part of S106 negoitiations | Ptarmigan is leading this. However, we she have this in mind for the s106 discussion and any possible endownment, |  | Ptarmigan have engaged with Mark Pratchett regarding early discussions on Stewardship. |  | 2024-08-01: August Update; 2024-09-01: No project update.; 2024-10-01: No project update.; 2024-12-01: No project update.; 2025-01-01: No project update; 2025-02-01: No project update; 2025-03-01: No project update; 2025-05-25: No project update; 2025-06-25: Stewardship is a key priority for Berinsfield Parish Council, and is being considered as part of the refocused Community Delivery Plan moving forward on how it can be progressed.
5 | Homes and infrastructure that meet local needs | Abbey Sports Centre Refurbishment | Complete | H | Complete the refurbishments of the wet side changing facilities and artificial turf pitch that are required to keep the Sports Centre in operational use until masterplanning commences and/or the community facilities project is complete and new/refurbished facilities are delivered. | SODC - Property and Leisure | 130000 | 130000 | 0 | SODC - S106 OCC | Wet side changing facilities refurshbishment complete in summer 2023. Works underway to renew the astro-turf pitch. To be completed by January 2024. | The new artificial turf pitch (ATP) for 5-a-side football was opened on 8 January 2024. The facility cost £179,647 paid by developers contributions and is now bookable via the Better UK website or through the Abbey Sports Centre. | Project complete. | Project complete. ACTION: Expansion of swimming pool - HK to follow with OCC and Ben Whaymand on options. LE20 budget that can support this piece of work | Expansion of swimming pool - HK to follow with OCC and Ben Whaymand on options. Looking at end Summer for final options / conclusions NW to confirm final deadline LE20 budget that can support this piece of work. What is the next steps? |  | The wet side changing facilities and artificial turf pitch are now refurbished and in use. The Sports Hall floor resurfacing will commence in July 24. We have identified budget to advance a RIBA Stage 0, Business Case for expanding the swimming pool at Abbey Leisure Centre. |  | 2024-08-01: August Update; 2024-09-01: Procurement is currently underway to appoint a consultant to advance a project to look into the expansion of Abbey Leisure Centre following recommendations from the district-wide Leisure Needs Strategy and Community Hub Feasibility Study. The work will support us in understanding the viability, technical and spacial requirements of proposals and project outcomes will follow RIBA Stages 0-3.; 2024-10-01: PMP is currently being circulated for feedback on the proposed specification to advance a project to look into the expansion of Abbey Leisure Centre following recommendations from the district-wide Leisure Needs Strategy and Community Hub Feasibility Study. The work will support us in understanding the viability, technical and spacial requirements of proposals and project outcomes will follow RIBA Stages 0-3.; 2024-12-01: Please see update in project 3.; 2025-01-01: Please see update in project 3.; 2025-02-01: Please see update in project 3.; 2025-03-01: Please see update in project 3.; 2025-05-25: Please see update in project 3.; 2025-06-25: OCC and SODC have progressed discussions around the Joint Use Agreement of Abbey Sports Centre, in light of Local Govenment Reorganisation. This means overdue works to the sports centre flooring and MUGA can now be undertaken.
6 | Homes and infrastructure that meet local needs | Neighbourhood Development Plan | Complete | H | Berinsfield Parish Council are producing a Neighbourhood Development Plan to ensure future developments meet the needs of the community, including some support and funding from SODC.Update summary | Berinsfield Parish Council | 0 | 0 | 0 | BPC - Locality | Regulation 14 pre-submission consultation of the Neighbourhood Plan opened for six weeks from 25th September to 20th November 2023. The consultation has now been extended for a further two weeks. | The PC has considered representations submitted in response to the statutory Regulation 14 consultation. The draft NDP has been updated by the PC's consultant. The PC shared the updated NDP with the district council on 15 January and asked for comments on the proposed changes. | Garden Communities Team and Place team, provided comments on the Pre Submission Respondse | The Berinsfield NDP group have sent an updated version of their plan for us to review. As we were going through the plan we noticed in particular that Policy BERIN 18 (page 23) might be something that you may wish to comment further on. NW to liaise with AS on response. ACTION: to share comments for amendments from SODC to NDP. To consider design code? NW to share Marta's details - SODC Urban Designer | The PC is continuing to refine the draft plan following the feedback from the consultation. They have produced Basic Conditions and Consultation statements. They are now producing a policies map. The latest estimate is that the draft plan will be formally submitted to us in mid May. |  | The Berinsfield NDP group have sent an updated version of their plan for SODC to review, following the Reg 14 pre-submission consultation. Berinsfield Parish Council received a grant from SODC of £7,000 to progress the NDP. SODC have sent the Berinsfield NDP group a draft version of the plan that incorporates the changes highlighted by SODC at Regulation 16. They are now finalising the document for submission. We do not have a submission date at this stage. |  | 2024-09-01: The publicity period on the draft plan concluded on 12 September. The draft plan documents and comments received during the publicity period have now been submitted for independent examination. Andrew Ashcroft has been appointed by the district council to carry out the examination. The examiner has issued a Clarification Note, which sets out initial comments on the submitted development plan and areas where further clarification would be helpful.; 2024-10-01: The publicity period on the draft plan concluded on 12 September. The draft plan documents and comments received during the publicity period have now been submitted for independent examination. Andrew Ashcroft has been appointed by the district council to carry out the examination. The examiner has issued a Clarification Note, which sets out initial comments on the submitted development plan and areas where further clarification would be helpful.; 2024-12-01: The independent examination of the Berinsfield Neighbourhood Development Plan has now concluded. Following careful consideration of the examiner’s recommendations, the council has determined that, with the changes recommended by the examiner, the plan meets the basic conditions and should proceed to a referendum. The referendum is scheduled to take place on Thursday, 6 February 2025.; 2025-01-01: The referendum is being held on Thursday 6 February at St Mary and St Berin Church; 2025-02-01: The Berinsfield Neighbourhood Plan became part of the Development Plan on 6 February 2025 and carries full weight in the determination of planning applications. On 13 February 2025 it was agreed to be made and that it should continue to be part of the development plan.; 2025-03-01: Following a 65.3% "yes" vote at the referendum on 6 February 2025, the Berinsfield Neighbourhood Plan became part of the Development Plan, carrying full weight in planning decisions. On 13 February 2025, the Council formally made the plan, confirming its continued status within the Development Plan.; 2025-05-25: Following a 65.3% "yes" vote at the referendum on 6 February 2025, the Berinsfield Neighbourhood Plan became part of the Development Plan, carrying full weight in planning decisions. On 13 February 2025, the Council formally made the plan, confirming its continued status within the Development Plan.; 2025-06-25: This project is now complete. Following a 65.3% "yes" vote at the referendum on 6 February 2025, the Berinsfield Neighbourhood Plan became part of the Development Plan, carrying full weight in planning decisions. On 13 February 2025, the Council formally made the plan, confirming its continued status within the Development Plan.
7 | Homes and infrastructure that meet local needs | Affordable Low Carbon Home Studies | Complete | M | Commission a study into affordable carbon friendly homes on existing sites within Berinsfield parish, which could explore communal living units, single occupancy homes, modular homes and managed affordable self-build plots. It will also involve researching eco-friendly techniques and principles, in line with the Council’s policies regarding the climate change emergency | SODC - BGV/Affordable Housing Registered Providers | 15000 | 14970.05 | 29.95 | SODC - BGV | Not yet started. | Not yet started. | Not yet started. | This may be something we redirect funding from to pursure an updated afforable housing needs assesment to inform the S106. In speaking with LP from Affordable Housing, we could look to do the following: Funding to obtain independent advice on the approach to help inform the S106 negotiations would be worthwhile – particularly if funding could be put toward an updated housing needs assessment. As we established at our recent discussion, aspiring to achieve a mixed and balanced community through potentially decanting occupants into the new development, but also levelling out tenures to provide a greater mix in Berinsfield (i.e., an increase in home ownership product) is likely to be difficult to balance. Therefore, if an evidence-based assessment can be conducted to establish an updated picture of need, this would provide a solid base to influence what weight should be given to which considered priority. | We need update the housing needs assessment from 2018. AS to explore procurement of this work. Revisit spec to understand what is required for the refresh work | A specification for a 2024 Housing Needs Assessment (HNA) has been developed a bid received from a potential supplier. The bid is currently being reviewed and assessed w/c 13 May. If bid accepted a contract will be put into place within the following few days. The specification and bid look at housing needs including afiordable housing with both 40% and 50% level within any new developmnent. | Housing Needs Assessment (HNA) contract agreed with sucessful bidder and initiation meeting held on 20 June. The specification and bid look at housing needs including affordable housing with both 40% and 50% level within any new developmnent. Draft report expected in August 24 and full report in September 24. The Health and Wellbeing Action Plan contains some draft actions related to retro fitting and reducing heating costs in existing homes and explotring renewable energy. |  | 2024-09-01: Appointed consultants Opinion Research have shared their initial draft report following the door-to-door survey in Berinsfield over summer 2024. Officers are currently reviewing the report for final revisions. There was a 21% response rate (227 completed questionnaires). Emerging findings include: - More than nine out of ten residents felt that their home met their current needs. However, those under the age of 40 and those in rented accommodation were significantly more likely to say their current home was not suitable. Reasons given for their current home not being suitable included having additional needs related to health or disability issues which often centred around accessibility, being over-crowding/not having enough space and a lack of parking spaces available. - Overall satisfaction with the area is high (73% satisfied) which is in-line with the 2019 survey results. The top reasons given for being satisfied include the local amenities (shops, pubs etc.), leisure facilities, and maintenance/tidiness of the area. However, similar proportions of residents felt that local amenities, and the maintenance/tidiness of the area could be improved along with parking, public transport and police presence/the level of crime. - Almost a quarter (23%) were looking to move within the next three years and most of these intended to stay fairly local either within Berinsfield or elsewhere in South Oxfordshire. Around one in ten wished to move to the new Mount Farm development. - One of the most common barriers to moving is cost (along with not being able to find a suitable home) with residents saying local house prices and rents are too high. Budgets were relatively low with only a half of those looking to move able to afford monthly housing costs of £750-£999 per month; 2024-10-01: Opinion Research are currently making final revisions to the report, following a final meeting on clariafications from the team.; 2024-12-01: A final draft report completed by ORS was received and will be circulated to the Steering Group at the next meeting in April. Evidence from this study will support the development of the Regeneration Strategy.; 2025-01-01: The final Affordable Housing Study report was received and this project is now complete.; 2025-02-01: The final Affordable Housing Study report was received and will be used to compile evidence that underpins the regnerations strategy. This project is now complete.; 2025-03-01: The final Affordable Housing Study report was received and will be used to compile evidence that underpins the regeneration strategy. This project is now complete.; 2025-05-25: The final Affordable Housing Study report was received and will be used to compile evidence that underpins the regeneration strategy. This project is now complete.; 2025-06-25: This project is now complete. The final Affordable Housing Study report was received and will be used to compile evidence that underpins the regeneration strategy. This project is now complete.
Community Health and Wellbeing | [11 empty] | January 2024 Update | 2024-02-01 | 2024-03-01 | 2024-04-01 |  |  |  | 2024-09-01: 2024-09-01; 2024-10-01: 2024-10-01; 2024-12-01: 2024-12-01; 2025-01-01: 2025-01-01; 2025-02-01: 2025-02-01; 2025-03-01: 2025-03-01; 2025-05-25: 2025-05-25; 2025-06-25: 2025-06-25
8 | Improved economic and community well-being | Community Grant Scheme | In progress | H | Roll out a community grant scheme for capital and revenue grants to fund community projects, services and initiatives to support community partners in delivering the best outcomes for Berinsfield residents. | SODC - BGV/Community Enablement | 345000 | 207341 | 137659 | SODC - BGV | Grant scheme launched in 2022, with subsequent successful awards announced in early 2023. Awards for both revenue and capital span between 1-5 year instalments until 2026. They are monitored annually against agreed targets by Grants Officers. | Officers have held mid-year monitoring meetings to review performance against their 2023/24 targets, with the organisations in receipt of a revenue grant. All organisations are performing well. 2024/25 payments will be released in May/June 24, following a monitoring meeting to review the end of year targets for 2023/24. |  | Update, same as January 2024. | Grants team are sending our monitoring forms to all grant recipients, could lead to new case studies | Grant scheme launched in 2022, with subsequent successful awards announced in early 2023. Awards for both revenue and capital span between 1-5 year instalments until 2026. They are monitored annually against agreed targets by Grants Officers. Annual monitoring round for the last financial year to start shortly. | Grant scheme launched in 2022, with subsequent successful awards announced in early 2023. Awards for both revenue and capital span between 1-5 year instalments until 2026. Officers are currently holding end of year monitoring meetings to review performance against their 2023/24 targets, with the organisations in receipt of a revenue grant. 2024/25 payments are being released once the satisfactory monitoring meeting has taken place. . |  | 2024-09-01: Grant monitoring was completed with stakeholders for expenditure and targets for the financial year 2023-24. Following Grants Officers meetings with participating groups, grant awards for 2024-25 are either in the process of being released or already have. Nine organisations in total were successful awarded multiple year funding between 3- 5 years, which included revenue and capital budgets.; 2024-10-01: We have a total of £32,292 outstanding for 2024/2025 within the Berinsfield Garden Village scheme across three organisations and we expect the full amount to be completed/ paid out within this financial year. - BGV22-23\15 – Riverside Counselling Service - £4,297 - BGV22-23\22 – The Berin Centre - £8,125 - BGV22-23\27 - Berinsfield Early Years Preschool - £19,870; 2024-12-01: We have a total of £30,143 outstanding for 2024/2025 within the Berinsfield Garden Village scheme across three organisations and we expect the full amount to be completed/ paid out within this financial year. Further scheduled allocations will be paid accordingly to organisations, following their annual monitoring. Further funding to support the Voluntary and Community Sector includes: 2025/2026 - £40,400 2026/2026 - £40,400; 2025-01-01: We have a total of £30,143 outstanding for 2024/2025 within the Berinsfield Garden Village scheme across three organisations and we expect the full amount to be completed/ paid out within this financial year. Further scheduled allocations will be paid accordingly to organisations, following their annual monitoring. Further funding to support the Voluntary and Community Sector includes: 2025/2026 - £40,400 2026/2027 - £40,400; 2025-02-01: All 2024/25 funding allocations are administered. Further scheduled allocations will be paid accordingly to organisations, following their annual monitoring. Further funding to support the Voluntary and Community Sector includes:; 2025-03-01: All 2024/25 funding allocations are administered. Further scheduled allocations will be paid accordingly to organisations, following their annual monitoring. Further funding to support the Voluntary and Community Sector includes: 2025/2026 - £40,400 2026/2027 - £40,400; 2025-05-25: All 2024/25 funding allocations are administered. Further scheduled allocations will be paid accordingly to organisations, following their annual monitoring. Further funding to support the Voluntary and Community Sector includes: 2025/2026 - £40,400 2026/2027 - £40,400; 2025-06-25: Annual monitoring is now underway, to allow administration of 2025/26 allocation to all grant receiptients. Further scheduled allocations will be paid accordingly to organisations, following their annual monitoring. Further funding to support the Voluntary and Community Sector includes: 2025/2026 - £40,400 2026/2027 - £40,400
9 | Improved economic and community well-being | Community Development | In progress | H | Recruit a Community Development and Outreach Officer who will work in Berinsfield to provide assistance for the needs of the residents, voluntary and community sector, businesses and other partners. The role will work closely with other Community Workers within Berinsfield with an engagement, outreach and development remit to compliment the wider offering and impact for residents. These may include (but not limited to), the Berin Centre, SOHA and CAG. | SODC | 35658 | 13555 | 22103 | SODC - BGV | Sarah Dodd successfully recruited and in place by January 2023. Agreement on extension to role agreed for another year to commence January 2024. | The current contract with the Berin Centre has come to an end. We are pleased how things have gone and both parties have learnt from the experience. We are reviewing resources with a view of sharing a joint officer across our Garden Communities at South and Vale in the future. |  | Recruitment of a new joint CDO with the DGT team has been advertised for three weeks. 10 applications received. Shortlisting will commence with interviews held end of March. | CDO now appointed and will be starting in June 2024. NW to confirm if the project description can be amended to reflect existing working situation …. | Emma will contact Wendy to negotiate salary and start date | By joint agreement with the Berin Centre, a decision was made for the Council to employ a Community Development Officer. A new Community Development Officer shared across the Garden Communities Team at South and Vale was successfully appointed following a recruitment process. The new post holder will commence in early August 24. | Recruited completed offer made. Wendy will start as the new CDO on 1 August 2024. | 2024-08-01: Wendy Foster started with SODC on 1 August 2024. The Berin Centre are currently advertising a number of roles.; 2024-09-01: Wendy Foster started her role as Community Development Officer with South Oxfordshire District Council on 1 August 2024. The Berin Centre have also recently recruited a Community Garden Coordinator and a Community Outreach Worker.; 2024-10-01: Links made with 11 businesses to develop CSR. Working relationships established with Berinsfield Community Association, the Berin Centre, the School Academy, the Pre-School, Age UK, the Health Centre, the Youth Centre, the Library and SOHA housing.; 2024-12-01: In December, Wendy engaged with 11 organisations in Berinsfield to establish and continue project work.; 2025-01-01: The CDO has been engaging with the residents regarding the Berinsfield Regeneration Strategy gaining feedback through face to face contact, QR codes, online and 2 drop in sessions; 2025-02-01: The CDO has a project plan in place for the launch of the Petanque, Skate Park and Pump Track. She is working closely with the clerk of the PC to improve Rugby, football and cricket on an inclusive basis. She has also met with Berinsfield Boxing Club and is supporting them to outreach into the community including Abbey Woods Academy and the Youth Centre with the help of Active Communities.; 2025-03-01: The CDO has project plans in place for the launch of new facilities including the Pétanque Court, Skate Park and Pump Track. She is working with the Berinsfield Lawn Games Group to help introduce the Petanque and Wallingford Petanque are supporting. She is working closely with the clerk of the PC to improve opportunities in rugby and cricket and fitness classes on an inclusive basis. Pilot sessions are being scheduled for the summer holidays.; 2025-05-25: A pump track and skate park launch is planned between 1st July and 22nd July before schools break. Oxfordshire Cricket are provided an Engagement Session at Abbey Woods Academy on 11 July. CDO has set up All Stars Cricket for 5-8 year olds and Dynamo Cricket for 8-11 year olds for 6 weeks from 23 July on the recreation ground. Street Cricket is starting permanently for 8 - 20 years old early evening tbc. Abbey Woods Academy have also signed up to the "Chance to Shine" 6 weeks cricket course for the whole school and teachers. CDO is also following up to provide Walking Cricket for Over 50's. CDO is liaising with Rugby Tots and West Wildcats (Touch Rugby) to try and start up Rugby sessions. A potential drama/dance session is being discussed to start at BCA. A staff member at BCA has come forward to talk to our Active Communites Team about leading some community sessions. The Petanque has a launch date on 5 June. Bersinfield Lawn Games Group are visiting Wallingford Petanque on 2 May to find out how to play the games.; 2025-06-25: All community development updates can be viewed against project 10, 11, 12, 14, 15, 16. The CDO will be engaging further with Abbey Wood Academy and the History Group to help co-create CIL funded projects. | Wendy is working with the Berin Centre and Abingdon and Witney College to design Arboriculture training to upskill volunteers. Wendy has also attending the reinstated Berinsfield Network meeting.
10 | Openness and accountability Improved economic and community well-being | Community Events | In progress | H | Throughout the year work with organisations to host community events and activities to improve health and wellbeing outcomes for residents, ensuring the Garden Villages Team have a strong presence to hear and keep the residents and community groups views engaged and updated with progress on the garden village. Utilise existing local communications channels to publicise events. | SODC - BGV | 10000 | 6852.5 | 3147.5 | SODC - BGV | Not yet started. Priority for roll out in 2024. | The team would welcome feedback on community events and activities that the Steering Group may wish to see in 2024 to support improved health and wellbeing outcomes for residents. New Year, New You event held at the BCA on 6 January, organised by Sarah Dodd. It showcased a variety of different taster sessions as part of the line up. |  | Programme events to be bought forward once the community development officer in place. Coordinating with the School and planting opportunities? Fete is on 27 July 2024 SOHA 27 March opening of the Community Garden | Identification and establishment of events that bring the community together has been identified as an action on the draft Health and Wellbeing Action Plan being developed by AS. The full budget (£10,000) is available for the new post to allocate to new events once they start. | The Health and Wellbeing Plan is being disseminated to the Berinsfield Health and Wellbeing Group for adoption and approval in w/c 13 May. Any actions for community events will be discussed and considered and actioned once the plan has received formal approval. | The Health and Wellbeing Plan has been developed and disseminated to the Health and Wellbeing Group and includes actions for community events, for action once the plan has received formal approval. The new Community Health Development Officer post holder staring 30 August will focus on this project as a priority. |  | 2024-09-01: The Health and Wellbeing Action Plan was completed and includes actions for community events. Wendy and Fazeelat would like to explore opportunities with wider partners to collaborate on this project.; 2024-10-01: Wendy has established links with Low Carbon Hub, National Energy Action and the National Energy Foundation (Better Housing Better Health) to discuss Energy Champion training for frontline workers. An update was provided in the Village Voice newsletter on our projects.; 2024-12-01: Wendy worked with the Low Carbon Hub to deliver training for organisations in Berinsfield and Didcot, to support front line services in addressing fuel poverty and client needs. Work is underway to plan for a careers convention in the village for Q4. Working with the Berin Centre, we've been able to help support a proposed event/workshops around food and culture. Working with the youth centre, we've also been able to support an event to celebrate all things wheeling as we anticipate the opening of the new community recreational areas in the Spring.; 2025-01-01: The CDO is working with the Health Centre and Berin Centre to roll out Energy Champion training this month in the community. A National Apprenticeship Week Campaign is being rolled out for 10 - 16 Feb.; 2025-02-01: The CDO reported that The Health Centre Energy Champion Trainer ran a session on 12 Feb for 10 people at the day care centre. The Berin Centre Energy Champion Trainer delivered an intro session on 12 Feb to the Over 60's and will be following this up with a formal one. The Manager of the Health Centre wrote a piece for the Village Voice and discussed the training at the Patient Participation Group meeting. Claire has had follow ups with her patients. National Apprenticeship Week campaign ran with daily helpful tips and a drop in CV session.; 2025-03-01: The CDO reported that following the upskilling event that took place in December 2024, the Health Centre Energy Champion Trainer ran a session on 12 Feb for 10 people at the day care centre. The Berin Centre Energy Champion Trainer delivered an intro session on 12 Feb to the Over 60's and will be following this up with a formal one. The Manager of the Health Centre wrote a piece for the Village Voice and discussed the training at the Patient Participation Group meeting. National Apprenticeship Week campaign ran with daily helpful tips and a drop in CV session. The CDO reported that the library and a local business would like to continue offering drop in sessions and there is one planned for Easter school holidaays.; 2025-05-25: Berinsfield Library displayed the Energy Champion resources during the Easter School holiday. A second careers drop session was held on 16 April in the library led by a HR Manager from a local business. A third session will be held as a pop up session alongside an outside community event during the Summer.; 2025-06-25: In June, a launch event was planned alongside SOHA to officially open the new petanque court. On the day we were joined by Wallingford Petanque Club and Berinsfield Lawn Games group. A launch event will go ahead on the 12 July with demonstrations including safety awareness to officially open the Skatepark and Pump Track. This includes intro safety events in Berry Youth Centre and Abbey Woods Academy on 8 and 9 July.
11 | Improved economic and community well-being | Healthy Place shaping | In progress | H | Develop a local Berinsfield profile and action plan to strengthen residents wellbeing and reduce the deprivation levels and health inequalities. This profile should also reflect and celebrate the community's great resources and strengths, in order to build and future proof services and assets. Ensure local partners endorse the strategy and take ownership of actions in areas of need. Complete benchmarking, annual monitoring and impact reports once the strategy is approved to ensure implementation and progress. Use the strategy and action plan to support joined up working and collaborative bids for external funding. | SODC - BGV OCC Public Health Team | 65000 | 51899 | 13101 | SODC -BGV OCC - PH | Project in progress. A new data profile for Berinsfield is now complete, which takes into account only the Berinsfield village boundary excluding Burcot and Dorchester. Stay Well Saturday event held on 21 October with various agencies to support engagement in the project and to provide advice to residents. Public survey on Health and Wellbeing closed on 3 November. Qualitative and quantative data analysis and coding now underway. The survey results, interviews with residents and organisations, focus groups and Steering Group feedback will be reviewed by our appointed independent consultant to help us develop the Community Insight profile in December. In early February we will start action planning with the Steering Group after reviewing the data profile and draft Community Insight report, to understand how we can tackle health inequalities. The action plan will be a multi-agency approach, to which organisations will agree to implement. £25,000 secured to either run a small grants scheme or direct award to help kick start action plan. Funding also ringfenced to appoint a part time Health Development Officer that will lead on the monitoring the implementation and outcomes of the action plan, encourage best practice and solutions on tackling health inequalities in service delivery, build capacity and provide support to others and report back with countywide colleagues to feed into the Oxfordshire Health and Wellbeing board. | The Community Insight profile is currently in draft form being developed. Engagement survey summary on health and wellbeing to be circulated. In early February we will start action planning with the Health and Wellbeing Steering Group after reviewing the data profile and draft Community Insight report, to understand how we can tackle health inequalities. The action plan will be a multi-agency approach, to which organisations will agree to implement. We will also hold three focus groups to help check in with the wider community to ensure it is on the right track. This will include speaking with young and older demographics. £25,000 secured to either run a small grants scheme or direct award to help kick start action plan - we're aiming for a launch date in July. Funding also ringfenced to appoint a part time Health Development Officer that will lead on the monitoring the implementation and outcomes of the action plan, encourage best practice and solutions on tackling health inequalities in service delivery, build capacity and provide support to others and report back with countywide colleagues to feed into the Oxfordshire Health and Wellbeing board. | Produce profile by 31 March 2024 within the FA. Timeline for grants launched for July in FA. AS working on focus group engagement materials - to be circulated by COP 09/02. 3 focus groups to be held on February 2024. Working with Fusion Arts and Active communities to see how they can support engagement with ADCC. Only to hold the evening engagement workshop at the Berin Centre. HK to look at obtaining HUG vouchers for incentives for engagement workshops. | Two H&W Steering Group meetings held to start discussing action planning against themes and headlines that came through community engagement. FA still not resolved with OCC, AS reviewed final position from OCC on our recent request and has escalated to JB to understand how we can accept any risk to move forward. Jayne has gone back to instruct legal to progress/advice further. Legal has been instructed further, SODC to agree final amends. NW to raise PO Grants research - it is being proposed that the Parish Council lead the community grants imitative. How do the PC operate already with grant aid? | AS currently advancing grant policy to outline the scheme to inform the parish council. The Insight profile is currently being review by OCC. Action planning has commence with stakeholders. The latest subgroup meetings were held on the 11 and 12 March to start action planning with stakeholders on how to address health inequalities following the recommendations and insights highlighted in the Community Insight Profile. The draft profile will be circulated in April 2024. The profile recommendations and action plan will outline a multi-agency approach, to which organisations will agree to implement it through new or existing projects, initiatives and activities. As part of launching the action plan, we are exploring with Berinsfield Parish Council how to open a community-led grants opportunity in July. We've ringfenced £25,000 for the health and wellbeing grants scheme. OCC have provided an updated Data Pofile for Berinsfield, but no substantive changes in the profile of Berinsfield have been identified. | The next meeting of the stakeholder group will take place on 21 May and will approve the Community Insight Profile and Aciton Plan and receive information on the Community Insight Profile Grants Scheme, which is set to commence in July 2024. Further work has been udertaken on the Berinsfield Grants Policy which is expected to be discussed at the Berinsfield Parish Council meeting on 13 May, at which it is anticpated that there will be a formnal endorsement by the Parish Council to adminster the scheme. | The Community Insight Profile ahas been finalised and circulated the Steering Group and Health and Wellbeing Group. An Aciton Plan have been further developed through health and wellbeing group workshops and consultation fromn May to June. A Grant Scheme policy has been developed and Berinsfield Parish Council formally agreed to faciltate the scheme at their June 24 meeting. The project is in the process of being formally approval by the Council and it is anticipated that the grant scheme will launch July 24. | The final draft of the community insight profile is undegoing final revisions. The Draft Action Plan is being review and condense where appropiate if outcomes overcross. | 2024-09-01: The Berinsfield Community Insight Profile which is inclusive of an Executive Summary, Data Report, Community Insight Report and draft Action Plan was co-produced and completed with the Health and Wellbeing Sub Group. The Sub Group included representatives from the voluntary and community sector, statutory and non statutory agencies, the parish council and residents. The profile is a multi-agency approach which outlines how each stakeholder or how as a collective we will tackle health inequalities in the village and also strengethen the great assetts and services which are already making a positive contribution to wellbeing. Its aim is to outline a strategy to help existing and new stakeholders with an invested interest to contribute to an agreed and targetted approach for the area. South Oxfordshire District Council approved the Profile and the transfer of £24,999 to Berinsfield Parish Council to administer a grant scheme in September 2024. The grant scheme was launched on 30 September. £250 - £5,000 will be available for eligible groups that submit bids that demonstrate how they or their project address the recommendations of the profile and action plan. The decision on the funding awards will be decided by a diverse grants panel, that include members from the parish council, residents, community representatives and officers. The Berinsfield Community Insight Profile was considered and noted by the Oxfordshire Health Improvement Board on 19 September. Lily Jones, Chair of the Berinsfield Health and Wellbeing Group and Youth Council attended with officers to introduce the item, answer questions and raise the status of the area amongst leading health organisations.; 2024-10-01: Transfer of funds to BPC now completed.; 2024-12-01: The Berinsfield Health and Wellbeing Grants Panel was held on Tuesday 3 December 2024. The decision on funding awards was decided by a grants panel, that includes members from the parish council, residents and community representatives and officers. 7 applications were received with a request of £32,402 meaning the scheme was oversubscribed (funding available £24,999). Ahead of the panel, individual members scored applications independently ahead of full moderation at the panel meeting to help decide the final allocated awards. In total, 6 applications were supported from the following organisations: The Berin Centre, Berinsfield Day Centre, Berinsfield Community Association, Berinsfield Pre School, Berry Youth Centre, Riverside Counselling. £20,815 of funding was administered before the end of the calendar year. A summary of submitted project themes (all aligning to purpose of grant in association with the Berinsfield Community Insight Profile and Action Plan): - Educational and upskilling support for children and young people - Support activities for those with special educational needs. - Male health, including mental health. - Mental health support for young people - Support and activities for the elderly to help reduce isolation. - Physical and holiday activities - First aid training provision - Wellbeing awareness workshops - Intergenerational projects The next Health and Wellbeing working group will be held on the 22 January 2025.; 2025-01-01: In total, six applications were supported by the Community Grant Panel, in line with the recommendations from the Community Insight Profile. They include The Berin Centre, Berinsfield Day Centre, Berinsfield Community Association, Berinsfield Pre School, Berry Youth Centre, Riverside Counselling. £24,999 of funding was administered. A summary of submitted project themes: - Educational and upskilling support for children and young people - Support activities for those with special educational needs. - Male health, including mental health. - Mental health support for young people - Support and activities for the elderly to help reduce isolation. - Physical and holiday activities - First aid training provision - Wellbeing awareness workshops - Intergenerational projects The next Health and Wellbeing working group to be held on 6 February. Commision work underway to focus on bringing services to the village to bridge the gaps in the following areas: primary school nutritional education, drug and alchohol support, SEND support.; 2025-02-01: The Health and Wellbeing working group was held on 6 February. The next meeting is on the 19 March 2025, with a focus on mental health and fuel poverty as 'spotlights'. The team are currently working with multiple agencies and community organisations to implement the actions identified in the plan. The team have also been instrumental in commissioning and liaising with several new services to bring them forward in the village to address identified need. They include: • Nourish and Flourish School Programme in partnership with SOFEA and Abbey Woods Academy. The programme focusses on providing preventative support for young people. Improving diet and understanding our nutritional needs is crucial for long term health. Integrating nutrition within the primary curriculum (for year 5) including Maths, Biology, Geography and History. Providing teachers with the lesson plans, slide decks and activity resources. Students are given an opportunity to learn to cook. The SOFEA whole system approach is used to support the school community. (FULLY FUNDED BY SODC) • Turning Point satellite provision within Berinsfield, to provide more accessible support for those struggling with alcohol and substance misuse. • Bringing together a SEND peer support group to support parents and carers following feedback, allowing them to have access to specialist advice. • Working with all H&W grants recipients to ensure their successful projects are underway.; 2025-03-01: The Health and Wellbeing working group was held on 19 March 2025, with a focus on fuel poverty and SEN as 'spotlights'. The team are currently working with multiple agencies and community organisations to implement the actions identified in the plan. The team have also been instrumental in commissioning and liaising with several new services to bring them forward in the village to address identified need. They include: •Nourish and Flourish School Programme in partnership with SOFEA and Abbey Woods Academy. The programme focusses on providing preventative support for young people. Improving diet and understanding our nutritional needs is crucial for long term health. Integrating nutrition within the primary curriculum (for year 5) including Maths, Biology, Geography and History. Providing teachers with the lesson plans, slide decks and activity resources. Students are given an opportunity to learn to cook. The SOFEA whole system approach is used to support the school community. (Fully funded by SODC) •Turning Point satellite provision within Berinsfield, to provide more accessible support for those struggling with alcohol and substance misuse. The CDO reported that regular sessions are starting in the Summer at the church. • Coordinating external agencies to bring forward additional capacity to build on a variety of SEND peer support groups to aid parents and carers following feedback, allowing them to have access to specialist advice and information. • Working with all H&W grants recipients to ensure their successful projects are underway.; 2025-05-25: Turning Point are confirming dates to start sessions in the Summer at the church. The CDO has met with the Good Neighbourhood Scheme Lead for Oxfordshire and is in discussion the restart the previous Volunteer Driver/Information Scheme into a Good Neigbourhood Scheme as demand is still required for residents. CDO and HWO met with Wallingford Draughtbusters on 2 April which comes under CAG Wallingford. We could signpost people to Draughtbusters through a Berinsfield Good Neighbourhood Scheme. The CDO has introduced the Headteacher form Abbey Woods Academy to the Berinsfield Boxing Club who are now applying to OCC for alternative provision so they can provide support for recognised students. They also met with Abingdon Gymnastics Club (in Berinsfield) who can provide SEND places on their courses. The next SEND film night at the BCA is on 18 May and the group is gaining members.; 2025-06-25: A further £25,000 has been secured through UKSPF to concentrate on health and wellbeing outcomes in 2025/26. It is proposed to use this funding in an hybrid approach through a small grants scheme and direct commissioning to implement priorities of the health and wellbeing action plan, subject to internal approvals. The Health and Wellbeing sub group met on 27 May. The next meeting will be held on 29 July. The group explored development of the following areas: - Youth Mental Health Services - Access to Healthy Food - Improving Skills and Inclusive Employment - Over 60's Health and Wellbeing including the Good Neighbour Scheme Other key health and wellbeing outcomes include: - Turning Point provisions are now in place in Berinsfield to offer face to face support and advice for those affected by drugs and alcohol misuse. - Good Neighbourhood Scheme Lead for Oxfordshire is in discussion with SODC and BPC to restart the previous Volunteer Driver/Information Scheme into a Good Neigbourhood Scheme as demand is still required for residents. - SEND Support Group is underway to formalise as an independent group. A survey being compiled by the group to understand needs to help prioritise service delivery. - Smoke Free Oxon, bi-weekly clinics to roll out at the health centre - Cervical Screening and contraception education outreach to be rolled out to encrouage uptake. - Development of a free course for Berinsfield residents to improve skills, support and guide people into jobs that they are interested in and want. This will include a preparatory stage to empower potential participants with a confident mindset, followed by the main course. - British Sign Language introduced in the community for those of all ages with hearing loss and problems with hearing aids by a local business. Trial at Over 60's club 2 July.
12 | Improved economic and community well-being | Active Communities | In progress | H | Work with the Active Communities team to implement leisure and recreation activities within Berinsfield to improve participation rates. The offer should include a range of sporting activities to accommodate all abilities and encourage residents to get more active. | SODC - Active Communities Team | 5000 | 0 | 5000 | SODC - BGV | Active Communities team already operate in Berinsfield under BAU. Following the outcomes of the Health and Wellbeing project, we will work with the team to plan for targeted activities to support any desired outcomes or objectives. | Active Communities team already operate in Berinsfield under BAU. Following the outcomes of the Health and Wellbeing project, we will work with the team to plan for targeted activities to support any desired outcomes or objectives. | Active Communities team already operate in Berinsfield under BAU. Following the outcomes of the Health and Wellbeing project, we will work with the team to plan for targeted activities to support any desired outcomes or objectives. | Active Communities team already operate in Berinsfield under BAU. Following the outcomes of the Health and Wellbeing project, we will work with the team to plan for targeted activities to support any desired outcomes or objectives. | Profile will inform new activitie, HK to meet with Jo's team / brainstorming session / Active Communities need to feed into the Action Plan | They are aware and involved with the Action Plan, will attend public events, no real outcomes from attending their meeting, asked for support with the Arts Nature Trail and Spinney Development project - Will need some more conversations and follow up on Forest School and Community Gardens | The Active Communities team already operate in Berinsfield under BAU. Following the outcomes of the Health and Wellbeing project, we will work with the team to plan for targeted activities to support any desired outcomes or objectives. |  | 2024-09-01: Early project scoping of a Nature Trail to encourage people to get active is being explored and how it can tie in nicely with the new improvements to open spaces in the area including pocket parks and the BMX pump track The Active Communities team continue to run their usual weekly fitness programmes in Berinsfield which include YouMove, Community Walks, Men's Mental Health Football. Seasonal acitvities were also delivered including school holiday opportunties included children's Multisports and Skateboarding. .; 2024-10-01: Wendy has responded to resident need for a Clubbercise class.; 2024-11-01: Clubbercise will hopefully start in Jan 2025. I am pursing a location for a Men in Sheds project. Wendy looking at Cricket and Rugby; 2024-12-01: Working with partners, Wendy is currently exploring sports development for cricket and rugby provisions in the village. The team is also looking at ways to develop community programmes ahead of the new facilities opening in the Spring such as the Pétanque Court and BMX track.; 2025-02-01: The CDO has met with Berinsfield Boxing Club and will be supporting them to create new wellbeing and mental health links in the community e.g overcoming bullying, building self esteem.; 2025-03-01: Officers are working with Berinsfield Boxing Club to increase their outreach and offering into the community including Abbey Woods Academy and the Youth Centre. The CDO reported that young boxers are interested in leading some Active Communities sessions in the community such as the Outdoor Gym. The BCA have also put forward a staff member interested in upskilling to lead sessions such as Buggy Walks.; 2025-05-25: The CDO has introduced the Headteacher from Abbey Woods Academy to Berinsfield Boxing Club who are now applying to OCC for alternative provision. The Academy are arranging a date for students to visit and meet young successful boxers. We also met with Abingdon Gymnastics Club (in Berinsfield) who can provide provison for 24 children to have a full term of gymnastics to meet their curriculum but this is subject to school budget.; 2025-06-25: Officers have worked with the Oxfordshire Cricket Association, to launch the All Stars and Dynamo cricket summer camps for children aged 5-11 years old over the summer holidays. All places will be free for Berinsfield residents and will take place every Wednesday on the recreation ground. Rugby Tots for 18 months to 7 years courses are also being finalised. News sports provision working alongside the Active Communities team were introduced at Abbey Woods Academy. They include World Sports and Born to Move.
13 | Improved economic and community well-being | Community Calendar | In progress | H | Develop a local Community Diary System (accessible to all) to show what's on and when to develop community cohesion. | SODC - BGV | 0 | 0 | 0 | SODC - BGV | Completed and online. Developed by the Berin Centre and instructions pack rolled out to all. Hosted on a variety of different community organisation websites through Google Calandar. Can be found on the Parish Council website here: https://www.berinsfield-pc.gov.uk/ | Project completed. |  | Through recent engagement on the H&W project, it is understood that this may not be working as effectively. | Identifying a dedicated resource to update and manage the community caldender has been identfied as an action on the draft Health and Wellbeing Action Plan currently being developed by AS. | The continued maintenance of the diary system is an action on the Health and Wellbeing Action Plan. The next meeting of the Health and Wellbeing Group will take place on 21 May and will seek to approve the action plan and identify partners in a position to deliver the actions, including the maintenance of the diary system. | Project Complete. Completed and online. Developed by the Berin Centre and instructions pack rolled out to all. Hosted on a variety of different community organisation websites through Google Calandar. Can be found on the Parish Council website here: https://www.berinsfield-pc.gov.uk/ The improvement and continued maintenance of the diary system is an action on the Health and Wellbeing Action Plan with SODC. | The improvement and continued maintenance of the diary system is an action on the Health and Wellbeing Action Plan with SODC. | 2024-08-01: The improvement and continued maintenance of the diary system is an action on the Health and Wellbeing Action Plan with SODC.; 2024-09-01: The improvement and continued maintenance of the diary system is an action on the Health and Wellbeing Action Plan. This will be picked up through the Health and Wellbeing workstream on how it can be sustained and improved.; 2024-12-01: The improvement and continued maintenance of the diary system is an action on the Health and Wellbeing Action Plan. This will be picked up through the Health and Wellbeing workstream on how it can be sustained and improved. The Village Voice now includes an activities and events schedule within each edition.; 2025-01-01: The Community Diary was updated by the Berin Centre and in discussion with the Community Network meeting was agreed to be rolled out to the wider public.; 2025-02-01: CDO reported that the PC now also roll out the Berinsfield diary and the Garden Communities Team are inputting major events; 2025-03-01: The Community Diary was updated by the Berin Centre and is now hosted on various community platforms. The CDO reported that a QR link to the diary is proposed for the Community map.; 2025-05-25: The Community Diary was updated by the Berin Centre and is now hosted on various community platforms. The QR code will also be hosted on the new Community Map.; 2025-06-25: The Community Diary was updated by the Berin Centre and is now hosted on various community platforms. The QR code will also be hosted on the new Community Map.
14 | Improved economic and community well-being | Public Arts and Culture | In progress | M | Use the arts to enable engagement and support various community initiatives to identify solutions, celebrate heritage and achievements of Berinsfield. Produce a plan for community based public art projects in the existing village and also in the new development site through the mechanism of Community Arts Development. Exploration of the arts can enable themes of placemaking, identity/brand for Berinsfield and develop on existing work. | SODC - BGV/Arts Development | 32000 | 32000 | 0 | SODC - UKSPF | Community programming proposals approved by SODC for roll out in late 2023 and early 2024. Proposals include: - A Reminiscence Project - pride of place, celebrating the past, present and future, capture local stories and lived experences. Document the village through the eyes of the residents and communities. - Dance and exercise - improving health and social isolation for an aging population - Youth Art School to support young people and upskill - Art in the Community - to support and add value to existing events and local initiatives - Legacy projects and building capacity for local organisations | Jo Acty worked with the junior and teen groups last term and in the holidays at Berry Youth Centre to explore the theme of identity. Uptake with both groups was really good and great engagement with the older tenn group. Discussing the potential for it to continue. Discussions and links with the Ashmoleon Museum are currently being formed. Awaiting outcome of potential outreach in Berinsfield. Advertisement of commission for the Reminiscence project was published in November. Tenders well received from a variety of different artists including one local Berinsfield artist. It is likely a collective of artists will support the delivery of the Reminiscence project. |  | An update from AB was given to the Parish Coucnil on Monday 4 March on all activities occuring under the UKSPF funding. Apply for grant funding to get some specific arts created - opportunties to explore with AB | Arts community programming continue to be rolled out in Berinsfield. - A Reminiscence Project - pride of place, celebrating the past, present and future, capture local stories and lived experences. Document the village through the eyesof the residents and communities. - Dance and exercise - improving health and social isolation for an agingpopulation - Youth Art School to support young people and upskill - Art in the Community - to support and add value to existing events and local initiatives - Legacy projects and building capacity for local organisations The Berinsfield Bureau is now live on instagram to document the evolving project. A community arts day was held on Saturday 23 March, which included exploring landscapes of Berinsfield with artist Lisa-marie and sun printing with Laura. A documentary is also being created with residents of the village by film-maker Sam Mansell. | Working with Abi on a nature trail to link all the newly developed green spaces, waiting for confirmation of land use from Church, Parish Council / Abi working on quotes for posts and sculptures - all Fusion Arts projects / programmes are taking place | Arts community programming continue to be rolled out in Berinsfield. - A Reminiscence Project - pride of place, celebrating the past, present and future, capture local stories and lived experences. Document the village through the eyes of the residents and communities. - Dance and exercise - improving health and social isolation for an aging population - Youth Art School to support young people and upskill - Art in the Community - to support and add value to existing events and local initiatives - Legacy projects and building capacity for local organisations The Berinsfield Bureau is now live on instagram to document the evolving project. A community arts day was held on Saturday 23 March, which included exploring landscapes of Berinsfield with artist Lisa-marie and sun printing with Laura. A documentary is also being created with residents of the village by film-maker Samuel Mansell.Working with Arts Development Officer on a nature trail to link all the newly developed green spaces. Arts Development Officer working on quotes for posts and sculptures - all Fusion Arts projects / programmes are taking place. |  | 2024-09-01: The UKSPF funding has enabled increased creative activity of art projects in Berinsfield. The projects have not only enhanced the local cultural scene but also strengthened community bonds. The collaboration between Fusion Arts and the commissioned artists has created a vibrant and inclusive environment, celebrating Berinsfield! The projects reached over 351 participants in Berinsfield. Employed : 10 artists Delivered: 11 community arts sessions with different groups and at different events. Engaged 2 children and youth groups with ongoing weekly activity for over a 6 month period. Examples include: Lisa-Marie and Laura: Collecting images and stories engaging in workshops with groups: Memory Cafe, Library History Group, Berry Youth Club, Bingo, Day Centre, Community Larder, Multicultural Group, Graft Groups, Berry Centre. The groups collectively contributed to the Berinsfield Bunting and the Community Day gave Berinsfield gave residents the opportunities to share their stories and sense of pride and ownership in their surroundings. Samuel Mansell: Creating a short collaborative film interviewing residents and documenting life in Berinsfield. Samuel Mansell has created documentaries that capture the spirit and stories of Berinsfield. His films showcase the community's heritage and the positive changes brought about by UKSPF-funded projects, preserving local narratives for future generations. A shoqing of the film is currently being organised. Jo Acty: Jo is a highly respected youth arts tutor and artist running a creative studio for young people for 30 years, creating collaborative community murals and public art installations, involving community members in the creative process. Jo joined the Berry Youth Club providing weekly activity for children and young people. Building creative and communication skills, sefl confidence and self esteem through creativity. Hannah Fredsgaard: Multi-instrumentalist and sound artist has done a number of field recordings of life in Berinsfield to build a soundscape and an audio history. Next steps for the forthcoming year is to use connections with organisations, artist and local residents to create public artworks within the community, building skills and improving the surrounding environment for people in the area.; 2024-10-01: Wendy met with Fusion Arts and they will submit proposal to develop Nature Trail and Abbey Woods Spinney arts and education; 2024-12-01: Fusion Arts are currently working with community organisations to design and create murals and mosaic panels that will be placed in the public realm for residents to enjoy.; 2025-01-01: A showing of the Berinsfield short film will be held at the BCA on the 28 February. A mosiac and mural project is being led by Fusion Arts working with a variety of groups to produce public artwork to compliment the public realm. They include: Berin Centre, Day Centre, Youth Centre and Church.; 2025-02-01: The film screening of Berinsfield for Berinsfieldian's was shown at the BCA on Friday 28 February, which included a Q&A session with participants. The event was well attended. Mural and mosiac projects currently underway with several community groups across the village, in partnerhsip with Fusion Arts. Wood sculptures commissioned to be installed in all the new pocket parks to create a nature trail. Putting artist in touch with landowners.; 2025-03-01: The film screening of Berinsfield for Berinsfieldian's was shown at the BCA on Friday 28 February, which included a Q&A session with participants. The event was well attended. This will be published on YouTube. Mural and mosaic projects currently underway with several community groups across the village, in partnership with Fusion Arts. The final pieces will be installed at the Berin Centre, Berry Youth Centre and the Church. Wood sculptures commissioned to be installed in all the new pocket parks to create a nature trail. These are all now installed. Further works on the trail to continue into the new financial year. The CDO reported that a class at Abbey Woods Academy have already been on their own nature trail to find all 4 wood carvings and visit the Spinney Forest School.; 2025-05-25: The CDO is working on a Interpretation Panel for the Forest School to educate awareness of creatures and plants which will complement the Nature trail leaflet.; 2025-06-25: The CDO is working on a Interpretation Panel for the Forest School to educate awareness of creatures and plants which will complement the Nature trail leaflet. the CDO is working with BBOWT to look at the "Nature Buddies" scheme initiative for the Forest School Spinney, Church Garden, Berin Centre gardening project, SOHA wildflower area, allotments and other green spaces.
15 | Improved economic and community well-being | Community Advice Services | In progress | H | Investigate and map service provision for local residents and assess needs for advice services and promote service provision widely through various means | SODC - BGV | 0 | 0 | 0 | SODC - BGV | Mapping considered as part of the Health and Wellbeing project, which will help inform any gaps in provisions as part of that project. Citizen's Advice Bureau now running a satellite provision within Berinsfield following a successful award of SODC grant funding. Also great advice support services from CAP, that are located on a Tuesday at the Library. | Mapping considered as part of the Health and Wellbeing project, which will help inform any gaps in provisions as part of that project. Citizen's Advice Bureau now running a satellite provision within Berinsfield following a successful award of SODC grant funding. Also great advice support services from CAP, that are located on a Tuesday at the Library. No further update. |  |  |  | Legacy of this project will be picked up in H&W Action Plan for future delivery, however mapping of service provision is completed and grants awarded to CAB to provided advice services in Berinsfield. | Legacy of this project is addressed in the Health and Wellbeing Action Plan. However mapping of service provision is completed and grants awarded to CAB to provided advice services in Berinsfield. | Legacy of this project is addressed in the Health and Wellbeing Action Plan. However mapping of service provision is completed and grants awarded to CAB to provided advice services in Berinsfield. | 2024-08-01: Legacy of this project is addressed in the Health and Wellbeing Action Plan. However mapping of service provision is completed and grants awarded to CAB to provided advice services in Berinsfield.; 2024-09-01: Legacy of this project is addressed in the Health and Wellbeing Action Plan. However mapping of service provision is completed and grants awarded to CAB to provided advice services in Berinsfield.; 2024-10-01: Links establshed with NO LIMITS programme who can work with individual residents to develop CV, job opportunties, interview skills and wellbeing to engage in workforce.; 2024-12-01: Legacy of this project is addressed in the Health and Wellbeing Action Plan. However mapping of service provision is completed and grants awarded to CAB to provided advice services in Berinsfield.; 2025-01-01: No project update; 2025-02-01: No project update; 2025-03-01: No project update; 2025-05-25: No project update; 2025-06-25: Exploration of the Good Neighbourhood Scheme is underway. Also the possibility of reinstating the Residents Association.
Sustainability and the Environment | [11 empty] | January 2024 Update | 2024-02-01 | 2024-03-01 |  |  |  |  | 2024-09-01: 2024-09-01; 2024-12-01: 2024-12-01; 2025-01-01: 2025-01-01; 2025-02-01: 2025-02-01; 2025-03-01: 2025-03-01; 2025-05-25: 2025-05-01; 2025-06-25: 2025-06-25
16 | Protect and restore our natural world | Enhancing Green Space | In progress | M | Conduct a review of open spaces to look for opportunities to enhance the areas by planting trees, hedges, and wildflower on district owned land and produce a treescape report. Following the review, a phasing plan will need to be developed to help plan for any capital improvements. Implentation of any capital improvement should focus on available land owned by SODC, OCC and the Parish Council. | SODC - BGV/Climate Action | 15000 | 2400 | 12600 | SODC - BGV | OxTrees report for tree planting and biodiversity opportunities within the Berinsfield parish boundary complete. Next stage yet to be progressed. | Currently undergoing project scoping to understand what is required moving forward. In January, Hen Knouwds met with Kim Hall and Stuart Scott Ely to explore the possibilities to enhance areas within Berinsifeld. As part of the UK Shared Prosperity Funding secured by the Garden Communities team, we've started to plan for the implementation of pocket parks. The team have explored the idea with SOHA on parcels of their land, as well as other land ownership assets. There is a requirement for these projects to be deliverd by the end of 2024-25 financial year due to external funding constraints. | Meeting with OCC Tree Opportuntiy Officer. Meeting with HK to map out area and opportunities in Berinsfield. What are the gaps? | HK exploring a design codes for the village? Commissioning opportuntiy to bring this forward planting, green funiture, streets and gateways. Discuss with urban designers from Planning - Jake Bassett | Will be using some of these funds to pay for the Abbey Woods Spinney surveys. £725 - Ecological Report (Wild Oxfordshire), Aboricultural Report (OCC). Will raise a PO fo pay for both. A formal design code will not be created at this stage, instead the BGV steering group will act as a design panel. HK to create 'voting' options for steering group on benches next. NW to confirn if this budget could cover the design of the spinney space | Both surveys have been commissioned for the Spinney Development project, should receive them beginning June. Need to commmision Spinney Design next. | OxTrees report for tree planting and biodiversity opportunities within the Berinsfield parish boundary complete. SODC is currently advancing a project focussing on the Spinney with the Parish Council and OCC to make it a more formal and valued site of natural space. This will help influence project 18 and creating an opportunity to bring forward a forest school space to the area. Abbey Woods Spinney tree and ecological reports have been received which have been shared with BPC, Wild Oxfordshire, OCC and Leaves of Green. These reports will inform the design for Abbey Woods Spinney to determine essential tree work, planting opportunities for nature and people. Full specification for this space will be discussed at the next project meeting before we procure the landscaping design from Leaves of Green. £2,400 of this budget have been allocated to cover the cost for this work. |  | 2024-09-01: OxTrees report for tree planting and biodiversity opportunities within the Berinsfield parish boundary complete. SODC is currently advancing a project focussing on the Spinney with the Parish Council and OCC to make it a more formal and valued site of natural space. This will help influence project 18 and creating an opportunity to bring forward a forest school space to the area. Abbey Woods Spinney tree and ecological reports have been received which have been shared with BPC, Wild Oxfordshire, OCC and Leaves of Green. These reports will inform the design for Abbey Woods Spinney to determine essential tree work, planting opportunities for nature and people. The design for the Spinney is complete. This will inform phased stages of improvements to bring forward the Forest School but to also make part of the area more accessible.; 2024-10-01: Plans in place for Brush cutting on one side of the Spinney on 7 Nov and a volunteer clear up day on 16 Nov; 2024-12-01: Between January and February 2025, 21 trees will be planted in the village on OCC owned land.; 2025-02-01: Two Scots Pines were planted at Abbey Woods Spinney, 36 new trees planted on SODC land in Berinsfield, and Berinsfield Parish Council is about to plant six new trees on their land. As part of BNG for the skatepark and pump track construction, a further four trees will be planted on BPC land.; 2025-03-01: Two Scots Pines were planted at Abbey Woods Spinney, 36 new trees planted on SODC/OCC land in Berinsfield, and Berinsfield Parish Council is about to plant six new trees on their land. As part of BNG for the skatepark and pump track construction, a further four trees will be planted on BPC land. The CDO reported that the Forest School Leader at Abbey Woods School is interested in putting forward ideas along with the pupils for the wildflower area and using Willow and Silver birch for weaving.; 2025-05-25: The CDO is working on a Interpretation Panel for the Forest School to educate awareness of creatures and plants.; 2025-06-25: No further update.
17 | Protect and restore our natural world | Community Environmental Projects | In progress | M | Work with the community to identify and progress community environmental projects and provide support for these activities. | SODC - BGV/Climate Action | 20000 | 16784.53 | 3215.47 | SODC - BGV | Not yet started. Priority for roll out in 2024. Early ideas include another accessible community garden at land by the church. | In discussions with Sarah Dodd and the Rev Teresa to create another community garden by the Church on Green Furlong opposite the shops. Potentially to encompass the 'Men in Sheds' project. There is potential for this to be included in the scope for pocket parks. |  | Looking at costings for planters with the church site, bench, accessible path going thorugh the area. Trying to understand the possibilitites. Site visits completed. Teresea to apply for match funding. |  | Could support training to Active Communities Team / School / Berin Centre / Youth Club - training forest school teachers: 2 x Leader / 2 x Assistants £4,000 | To create capacity for outdoor education, £4,000 of this budget will be allocated to training forest school leaders and assistants. This is part of the Abbey Woods Spinney pocket park and forests school project. |  | 2024-09-01: To create capacity for outdoor education, funding is allocated for training to support representatives in becoming Forest School Leaders. We are also exploring upskilling opportunities for young people in Forestry and Arboriculture. This opportunity is open to ogranisations in Berinsfield.; 2024-10-01: Level 3 Forest School Leaders Award starts in Dec with potential candidates, the local School Academy Forest School Leader will attend a refresher in March. Talks with Abingdon and Witney College to provide an upskilling coure in Gardening and Arboriculture for residents; 2024-12-01: SODC are funding three places for representatives to obtain a qualification in Level 3 Forest School Leader which will commence in 2025. This will support utilising the space at Abbey Woods Spinney. The team are also working with Abingdon and Witney College to provide an upskilling course in Gardening and Arboriculture for residents.; 2025-02-01: Two residents are signed up to complete Forest School Leader training. Abbey Woods Acacdey Forest School Leader is attending a refresher training course in March ready to offer session over the summer.; 2025-03-01: Two residents are currently completing their Forest School Leader training. Abbey Woods Academy Forest School Leader completed their refresher training course in March ready to offer session over the summer. Budget supported advancement of the planning application requirements for all Biodiversity Net Gain (BNG) including the Habitat Management Plan (HMP) conditions for the Skatepark and pump track projects.; 2025-05-25: The CDO reported that the Forest School Leaders are progressing with their training. A group has been formed for all 3 Leaders to support each other to benefit the Forest School Spinney.; 2025-06-25: The CDO reported that the Forest School Leaders are progressing with their training. A group has been formed for all three Leaders to support each other to benefit the Forest School Spinney. Further upskilling opportunities through BBOWT are currently being explored which include the "Nature Buddies" initiative. CDO is also meeting with CAG to explore local status.
18 | Protect and restore our natural world | Forest School | In progress | L | Liaise with Oxfordshire County Council to ensure overgrown sections of the Spinney are cleared to stop brambles growing onto Abbey Woods Academy grounds. Once this is completed Berinsfield Parish Council intend to rent the land from OCC so it can be used for a Forest School. | OCC Berinsfield Parish Council | 0 | 0 | 0 | N/A | Work by OCC complete, other aspect of the project not yet started. | Work by OCC complete, other aspect of the project not yet started. However, this area may be considered to be part of project 16. |  | Gateway form being drafted - concept phase nearly completed to develop the project. April milestone for phasing and studies to be completed. | See UK SPF Spinney Development Pocket Park Plan | First stakeholder event to take place in June - still to be organised, surveys should be in place beginning June which will inform design. Procurement process for the design should start. SODC procure the design. Follow up on GW2 form with Nicole. | Work completed by OCC and BPC to clear the site of flytipping and rubbish. A DA requesting the transfer of UK SPF and an ICMD requesting the transfer of CIL funds to BPC to support the Abbey Woods Spinney Forest School project is currently delayed with Legal, impacting the delivery timeline of this project. BGV team is preparing to contract the design work to Leaves of Green in July. We have received the tree and ecological survey for the spinney to inform the design and ongoing maintenance plan for the space. Project specifications will be finalised at the next stakeholder meeting end of June. BPC will contract the construction work with the funding. |  | 2024-09-01: Berinsfield Parish Council has agreed to move forward with a volunteer build approach to implement the groundwork for the Abbey Woods Spinney enhancement and forthcoming Forest School. Over 20 residents, along other community organisations have offered to participate. Leaves of Green will be contracted to coordinate the materials, equipment, and volunteers on the agreed day. A volunteer day is currently being organised for Winter 2024. Relevant updates to support this project also cited in project 17 and 29. Budget allocated from project 17 and UKSPF.; 2024-10-01: Brush cutting is in place for 7 Nov and a Volunteer clear up day planned for 16 Nov; 2024-11-01: Volunteer Build Day took place on 30 Nov to remove some of the nettle roots; 2024-12-01: A Volunteer Build Day was held on 30 November 2024, to remove nettles and roots from Abbey Woods Spinney to support it in becoming an accessible and operational space. Tree works was granted permission in December 2024 by the Local Planning Auhtority, to proceed with tree maintenance including felling within in the Spinney which is protect by a Tree Protection Order. Crowning and felling of specific trees will take place in January 2025, ahead of other improvements to the space to help it become a Forest School. They will include wood sculptures, informal seating and an interpretation board.; 2025-01-01: A candidate began the Forest School Leaders Level 3 course on 1 Feb; 2025-02-01: A gathering space has been created in the southern section of Abbey Woods Spinney, providing ample room for forest school sessions. Timber from felled trees has been repurposed as seating, and a magnifying post has been installed. Additionally, two new Scots pines have been planted, and a wooden owl sculpture is set to be installed by 31 March.; 2025-03-01: Stage 1 construction of the design is nearly complete. Funding for Stage 2 sourced and plans underway including an archway with weaved in sticks, a dead hedge and removal of nettles growing to ensure safety and inclusiveness.; 2025-05-25: CDO is waiting for PC approval to go ahead with dead hedge and archway using a recycled trampoline. The PC are researching a longer term solution for removing the nettles so that Abbey Woods Academy can start Forest School lessons.; 2025-06-25: The CDO is working on a Interpretation Panel for the Forest School to educate awareness of creatures and plants. The CDO visited BBOWT who suggested including an interaction panel with the Interpretation board. Berinsfield Parish Council are currently leading on improvements for stage 2 of the Abbey Woods Spinney Project.
19 | Action on the Climate Emergency | Watercourse Enhancement | Not started | L | Complete a technical study into how the watercourse can be enhanced to address flooding by surveying the existing foul and surface water drainage systems. This study will be used to inform masterplanning due to flooding in specific areas. | Ptarmigan | 0 | 0 | 0 | N/A | To be considered as part of the planning application. | To be considered as part of the planning application. No further update. |  |  |  |  | To be considered as part of the planning application. No further update. | To be considered as part of the planning application. No further update. | 2024-08-01: To be considered as part of the planning application. No further update.; 2024-09-01: To be considered as part of the planning application. No further update.; 2024-12-01: To be considered as part of the planning application. No further update.; 2025-01-01: To be considered as part of the planning application. No further update.; 2025-02-01: To be considered as part of the planning application. No further update.; 2025-03-01: OCC Engineer has recently coordinated maintenance clearing. Further improvements to be considered as part of the planning application by Ptarmigan. No further update.; 2025-05-25: OCC Engineer has recently coordinated maintenance clearing.; 2025-06-25: OCC Engineer has recently coordinated maintenance clearing. No further udpate.
20 | Action on the Climate Emergency | Community Energy | Complete | H | To undertake a feasibility study on opportunities for developing land or building-based energy assets within the Berinsfield Parish area that will be owned by members or organisations of the community. The feasibility study will focus on renewable and low carbon assets. It is envisaged that any community energy project, will also support the commitment to ensure the local services and organisations within the parish remain sustainable. We anticipate that if there are viable opportunities to deliver community energy projects within the parish, this may link into the wider proposals and stewardship of a new or regenerated community hub. | SODC - BGV/ Economic Development | 9500 | 9500 | 0 | SODC - UKSPF | Stage 1 feasibility study commissioned and completed by The Low Carbon Hub. Headline findings include commercial roof mounted solar PV, field array PV and water source heat pumps at Queenford Lakes. Briefing report on the work completed to date and next steps will be considered by South Oxfordshire Climate and Ecological Emgencies Advisory Committee on 11 December ahead of any recommendations being considered by South Oxfordshire District Council's Cabinet. | Briefing report on the work completed to date and recommendations will be considered at South Cabinet Briefing on 23 February. The team are exploring with OCC whether the project can be considered as a candidate for the smart community energy scheme (SCES) to support it being developed further. |  | Cabinet briefing report completed internal consultation. Aiming for cabinet briefing in April. Report needs to go to SMT for sign off. BETA Phase funding opportunity being bidded for by OCC. |  | This project will be moved forward by the Climate Team before a final decision can be made | SODC member briefing to outline work completed to date and gain steer from members is progressed. Internal consultation at SODC completed. BETA Phase funding opportunity bid made by OCC, to support community energy projects developed further. Outcomes of the external funding opportunity not yet announced. This project will be moved forward by the Climate Team before a final decision can be made. The Health and Wellbeing Action Plan includes draft actions which will contribute to renewable energy projects. |  | 2024-09-01: As recommended in the initial desktop study report developed by the Low Carbon Hub, the delivery of a water-source district heat network at Queenford Lakes would provide clean renewably generated heat to the 1089 existing homes in the village and the 1700 proposed new homes. Round 14 of the Heat Network Delivery Unit recently opened. This Department for Energy Security and Net Zero (DESNZ) scheme offers up to 100% funding for heat network project development. Alongside the Climate Action team, we've supported the development of a bid to support commissioning expert consultants to conduct the next stage of feasibility work. This bid was supported in consultation with the landowner.; 2024-10-01: No project update. Wendy has worked with Low Carbon Hub to promote their Business Energy Audit and to date Williams Jet Tenders and Abingdon Gymnastics Club (based in Berinsfield) have successfully completed their audit.; 2024-11-01: Low Carbon Hub Energy training taking place on 5 Dec with 16 candidates (half from Berinsfield); 2024-12-01: A funding bid was submitted in December 2025 to a grant scheme being run by the Greater South East Net Zero Hub called the Investment Readiness Hub. This application is to help us progress the next stage of feasibility work on a water sourced heat-pump scheme at Queenford Lakes Berinsfield. As recommended in the initial desktop study report developed by the Low Carbon Hub, the delivery of a water-source district heat network at Queenford Lakes would provide clean renewably generated heat to the 1089 existing homes in the village and the 1700 proposed new homes. This bid was supported in consultation with the landowner.; 2025-01-01: No project update; 2025-02-01: Awaiting outcomes of the submitted bid to a grant scheme being run by the Greater South East Net Zero Hub called the Investment Readiness Hub.; 2025-03-01: We were unsuccessful in our bid to Greater South East Net Zero Hub called the Investment Readiness Hub for the next phase of feasibility for the Comunity Energy project. The IRS grant received significant interest across the Greater South East, with 26 applications submitted worth more than £1.7 million. The IRS funding pot totalled £750k, so the grant was extremely competitive. Key eligibility criteria were that the project could reach investment readiness within two years and that there are no other more suitable funding streams available. We have had a follow up meeting our contact at the Great South East Net Zero Hub and agreed a plan to move forward with applications to the Heat Network Delivery Unit (HNDU) funding scheme, which is not yet open but is a cyclical funding opportunity. This scheme requires less detail than the Investment Readiness Scheme, so we have already done the bulk of the work required to apply for funding for Berinsfield Heat Network Feasibility Study and will be considering whether to develop proposals for Heat Network Feasibility Studies at proposed other sites in the district.; 2025-05-25: £9,000 secured through UKSPF to progress a Stage 2.; 2025-06-25: Stage 1 Feasibility Study of this project is complete. A further £9,000 has been secured through UKSPF for 2025/26 to progress to Stage 2. This will be advanced working alonsided our Climate Action team.
21 | Action on the Climate Emergency | Decarbonisation Audits | Complete | H | Produce a decarbonisation report for each of the five community facilities audited . Identify measures, including low and zero cost measures, energy efficiency upgrades, low carbon heating options and on-site renewable energy generation. Calculate the energy and carbon savings. Undertake preliminary economic modelling. | SODC - BGV/Economic Development | 7350 | 7350 | 7350 | SODC - UKSPF | Decarbonisation audits completed on five community buildings in Spring 2023 that outlined recommendations for improvements. As part of wider UKSPF secured for the Garden Communities team, £59,000 is ringfenced to support community organisations in implementing some capital improvements work towards decarbonisation targets. Organisations will be notified of itemised grant awards in Winter 2023. | As part of wider UKSPF secured for the Garden Communities team, £59,000 is ringfenced to support community organisations in implementing some capital improvements work towards decarbonisation targets. Organisations will be notified as soon as possible. Small delay on notification due to pending internal approval. |  | Decarbonisation capital funding awards now shared with successful organisations. Award letters, T&Cs, PO administered. PC allocations over 25k and will be a key decision. Action: shared user guide to comms and UKSPF |  | Report is completed / keep open till 2025 | As part of wider UKSPF funding secured for the Garden Communities team, a further £59,000 is ringfenced to support community organisations in implementing capital improvements towards decarbonisation targets following the audits completed last year. Organisations are now notified of grant allocations and will received funding following receipt of signed documentation. All improvements to be implemented by March 2025. |  | 2024-09-01: Five audits completed on community organisations in Berinsfield. Organisations are now notified of grant allocations and will received funding following receipt of signed documentation. All improvements to be implemented by March 2025. Further funding from UKSPF to offer free decarbonisation audits were launched in September. Wendy has visited all businesses in Berinsfield to notify them of the opportunity.; 2024-10-01: Final DA to award BPC allocated award for improvements to the Pavilion in internal consultation.; 2024-12-01: The final grant funding award to Berinsfield Parish Council to be administered in January 2024, to progress recommendation in their decarbonisation audit on the Pavilion. All other capital decarbonisation improvements underway at the BCA, the Berin Centre and Berry Youth Centre.; 2025-01-01: All capital decarbonisation improvements underway at the Pavilion, BCA, the Berin Centre and Berry Youth Centre.; 2025-02-01: All capital decarbonisation improvements underway at the Pavilion, BCA, the Berin Centre and Berry Youth Centre.; 2025-03-01: All capital decarbonisation improvements underway at the Pavilion, BCA, the Berin Centre and Berry Youth Centre.; 2025-05-25: The pavilion solar projet has been out been out to tender, selected a contractor and had meetings on site. The DNO is being applied for.; 2025-06-25: Decarbonisation workstreams of this project is now complete. Berinsfield Parish Council is leading on the pavilion solar project. They've been out to tender, selected a contractor and had meetings on site. The DNO is being applied for.
Active Travel | [11 empty] | January 2024 Update | February 2024 | 2024-03-01 |  |  |  |  | 2024-09-01: 2024-09-01; 2024-10-01: 2024-10-01; 2024-12-01: 2024-12-01; 2025-01-01: 2025-01-01; 2025-02-01: 2025-02-01; 2025-03-01: 2025-03-01; 2025-06-25: 2025-06-25
22 | Action on the Climate Emergency | Roman Road Cycle Route | In progress | M | This project is led by Oxfordshire County Council to create a new cycling network from Berinsfield to north Oxford as part of their countywide active travel plan. | OCC | See notes. | 0 | 0 | OCC | OCC were successful in securing £10.5m in Active Travel Tranche 3 funding to progress a variety of projects across Oxfordshire. One of the projects that will be progressed as part of this tranche will be the development and design of Berinsfield to Oxford. The project looks at two options for a walking and cycling route between Berinsfield and Oxford (Cowley), the Roman Road using PROWs, and an option along the A4074. | Update requested to be bought to future BGV Steering Group meeting. OCC were successful in securing £10.5m in Active Travel Tranche 3 funding to progress a variety of projects across Oxfordshire. One of the projects that will be progressed as part of this tranche will be the development and design of Berinsfield to Oxford. The project looks at two options for a walking and cycling route between Berinsfield and Oxford (Cowley), the Roman Road using PROWs, and an option along the A4074. OCC have been invited to the 1 July Steering Group meeting to provide an update on progress. |  | Sam is outstanding with BGV meetings actions - 10 April is next steering group. Angela to now admistered the BGVSG meeting dates and associated planning meeting for the calendar year. |  | NW to follow up with OCC for update on RR Cycle Route at next Steering Group meeting | OCC were successful in securing £10.5m in Active Travel Tranche 3 funding to progress a variety of projects across Oxfordshire. One of the projects that will be progressed as part of this tranche will be the development and design of Berinsfield to Oxford pedestrian and cycle route. The project looks at two options for a walking and cycling route between Berinsfield and Oxford (Cowley), the Roman Road using Public Rights Of Ways, and an option along the A4074.OCC have been asked to provide an update at the next Steering Group meeting. | Procurement out for tender. | 2024-09-01: A procurement exercise to appoint a consultant to develop the design of the two schemes is complete and the project has commenced. The project looks at two options for a walking and cycling route between Berinsfield and Oxford (Cowley), the Roman Road using Public Rights Of Ways, and an option along the A4074. As the design stages progress, stakeholder engagement will be scheduled.; 2024-10-01: No project update.; 2024-12-01: The design and feasibility study is still underway. OCC will provide a project update at the April 2025 Steering Group meeting.; 2025-01-01: The design and feasibility study is still underway. Transport modelling data currently being collected.; 2025-02-01: Phil Jones Associates working with Sustrans have been appointed to carry out the feasibility work for the Berinsfield to Oxford Cycle routes. Both the Roman Road off-road route and the A4074 route are being studied and feasibility level plans will be developed for both routes. To date the work has focussed on data collection and site visits. However, design options will be developed in the coming 6 weeks.; 2025-03-01: Feasibility work is underway on the Berinsfield to Oxford Active Travel Scheme. Two alignments are being developed: - Largely off-road following existing bridleways and the Roman road between north of Berinsfield and Grenoble Road - Alongside the A4074 between Berinsfield and Grenoble Road. Feasibility work includes surveys, land ownership, access requirements for all users and other assessments. Final options for both alignments will be drawn up and work should be complete in June 2025. Further detail on the options can be shared with the steering group for discussion and feedback in the next meeting.; 2025-06-25: Feasibility work is underway on the Berinsfield to Oxford Active Travel Scheme. Two alignments are being developed: - Largely off-road following existing bridleways and the Roman road between north of Berinsfield and Grenoble Road - Alongside the A4074 between Berinsfield and Grenoble Road. Feasibility work includes surveys, land ownership, access requirements for all users and other assessments. Final options for both alignments will be drawn up and work should be complete in July 2025.
23 | Action on the Climate Emergency | Localised Active Travel and Public Transport Study | Not started | L | Commission a transport study to look at light weight and short distance mobility in and around the village, specifically focusing on connectivity to key bus stops. Inclusion of all electric and active travel modes. This will produce recommendations for a pilot scheme. | SODC - BGV | 25000 | 0 | 25000 | SODC - BGV | Not yet started. | Not yet started. |  | Not yet started. |  | Not yet started. | Not yet started. | Not yet started. | 2024-08-01: Not yet started.; 2024-09-01: Not yet started.; 2024-10-01: Not yet started.; 2024-12-01: Not yet started.; 2025-01-01: Not yet started.; 2025-02-01: The newly appointed BGV project officer will start scoping out this project. She will research current transport picture of Berinsfield, drawing data from various reports as the first stage of scoping. She will research localised active travel 'best practice' in other Garden Village / Town developments we could look at replicating in Berinsfield. Her scoping will include options for short, medium and longer term implementation. This will all be considered wether or not the new development takes place.; 2025-03-01: Project scoping underway. Research of the transport picture of Berinsfield, trends and drawing data from various reports as the first stage of scoping. Research will also include localised active travel 'best practice' in other Garden Community developments we could look at replicating in Berinsfield. Scoping will include options for short, medium and longer term implementation. This will all be considered whether or not the new development takes place.; 2025-06-25: No yet started.
24 | Action on the Climate Emergency | Active Travel Schemes | Not started | L | Provide funding for technical studies required by Oxfordshire County Council Transport Strategy Team to undertake optioneering and some feasibility design across key walking and cycling routes, Berinsfield to Oxford and Berinsfield to Culham Science Centre (which in turn links to Abingdon and Didcot). | OCC | TBC | 0 | 0 | OCC | Not yet started. | Not yet started. | Not yet started. | Not yet started. | Not yet started. | Not yet started. | Not yet started. | Not yet started. | 2024-08-01: Not yet started.; 2024-09-01: Not yet started.; 2024-10-01: Not yet started.; 2024-12-01: Not yet started.; 2025-01-01: Not yet started.; 2025-02-01: Not yet started.; 2025-03-01: Not yet started.; 2025-05-25: Not yet started.; 2025-06-25: Please see project 22.
Governance and Legacy | [11 empty] | January 2024 Update | February 2024 | March 2024 |  |  |  |  | 2024-09-01: 2024-09-01; 2024-12-01: 2024-12-01; 2025-01-01: 2025-01-01; 2025-02-01: 2025-02-01; 2025-03-01: 2025-03-01; 2025-06-25: 2025-06-25
25 | Openness and accountability | South and Vale Garden Communities Steering Group Meeting | In progress | M | Agree Terms of Reference (ToR) for the new group and set up steering group and project meetings with key stakeholders to raise the profile of the Berinsfield Garden Village team. Ensure that the governance of the steering group and ToR represents a variety of different organisations and stakeholders in Berinsfield. Stakeholders may include (but not limited to); SODC, OCC, Berinsfield PC, Land agent/developer, Voluntary and Community sector, other core service providers, resident representation. This will ensure the work is in line with Garden Village principles and will also inform Berinsfield Parish Council and the wider community of all activity due to take place. | SODC - BGV | 1000 | 545 | 455 | SODC -BGV | On going, bi-monthly Steering Group meetings already taking place with key stakeholders involved. | On going, bi-monthly Steering Group meetings already taking place with key stakeholders involved. |  | Steering Group was held on the 10 April. Minutes to be approved. | Steering Group is now meeting on a quarterly basis, with meeting dates established until January 2025. teering Group was held on the 10 April. Minutes to be approved at the next meeting on 1 July 2024. | All Steering Group meetings have been established and draft minutes being prepared from the last meeting in April 2024. | Steering Group meetings have been established on a quarterly basis. |  | 2024-09-01: This is on going. The Berinsfield Garden Village Steering Group meets quarterly.; 2024-10-01: This is on going. The Berinsfield Garden Village Steering Group meets quarterly.; 2024-12-01: This is on going. The Berinsfield Garden Village Steering Group meets quarterly.; 2025-01-01: This is on going. The Berinsfield Garden Village Steering Group meets quarterly.; 2025-02-01: This is on going. The Berinsfield Garden Village Steering Group meets quarterly.; 2025-03-01: This is on going. The Berinsfield Garden Village Steering Group meets quarterly.; 2025-05-25: This is on going. The Berinsfield Garden Village Steering Group meets quarterly.; 2025-06-25: This is on going. The Berinsfield Garden Village Steering Group meets quarterly.
| Investment and innovation that rebuilds our financial viability | Alternative Funding Schemes | In progress | L | Research additional funding streams using Grant Finder to identify opportunities to obtain external funding to support and enhance the delivery of the garden village. | SODC - BGV | 0 | 0 | 0 | SODC -BGV | Not yet started. | Not yet started. | Not yet started. | Not yet started. | AS, please can we start conversations with Justin Andrews on exploring potential opportunities for external funding to advance projects. | A meeting with Justin Andrewes (External Funding Lead) took place at the beginning of May to explore potential opportunities for external funding to advance projects. It was advised that officers should start with smaller projects and build upon them and that Garden Communities Officers should firstly identify projects that the community want and that we can evidence they need which can be matched to external funding streams and their aims. It was agreed that Justin would hold a workshop with Garden Communities to outline the nature of developing strong funding bids and the discus the project ideas from the team. The timings of this workshop meed to be agreed but could perhaps happen post the completion of current recruitment processes and once the team is fully staffed. | Meeting held with External Funding Lead to explore external funding opportunities. A workshop will take place in late summer/autumn 24 to explore projects and initiatives from the Garden Communities Team and align to potential funding sources. |  | 2024-09-01: Working with the External Funding Lead at SODC, future opportunities are being explored to identify funding opportunities to help deliver the Berinsfield Community Delivery Plan. We received £50,000 from Home England for the 2023/24 award for capacity (revenue) funding to support delivery of the Berinsfield Garden Village Programme.; 2024-10-01: Working with the External Funding Lead at SODC, future opportunities are being explored to identify funding opportunities to help deliver the Berinsfield Community Delivery Plan. We received £50,000 from Home England for the 2023/24 award for capacity (revenue) funding to support delivery of the Berinsfield Garden Village Programme.; 2024-12-01: Ongoing review of funding opportunities to progress projects in Berinsfield.; 2025-01-01: Ongoing review of funding opportunities to progress projects in Berinsfield.; 2025-02-01: Berinsfield Garden Village Team was successful in securing CIL funding for the following three projects: • Berinsfield signage and amenities upgrade project - £92,413 This project seeks to revitalise the village by upgrading its infrastructure and enhancing its appearance. Key initiatives include replacing outdated street signs, bins, and welcome signs, refurbishing public benches, and installing a new youth shelter. A key focus is improving accessibility in Berinsfield parks by installing play equipment designed for children with Special Educational Needs and Disabilities (SEND), ensuring that all public spaces are safe, inclusive, and welcoming. This project will be delivered by the BGV Team in partnership with BPC. • Drainage of Berinsfield Sports Fields – £110,000 This project involves installing a drainage system on the recreation field. SODC plans to transfer these funds to BPC, allowing them to deliver the project independently. The transfer will be formalised through a funding agreement. Before moving forward, we need to seek approval through our internal decision-making process. • MUGA - £200,000 This project seeks to transform the outdated basketball court next to Abbey Sports Centre into a modern, multi-functional facility to better serve the community's needs. SODC is currently negotiating a Lease Agreement with OCC, which must be finalised before the project delivery can begin.; 2025-03-01: Berinsfield Garden Village Team was successful in securing CIL funding for the following three projects: • Berinsfield signage and amenities upgrade project - £92,413 This project seeks to revitalise the village by upgrading its infrastructure and enhancing its appearance. Key initiatives include replacing outdated street signs, bins, and welcome signs, refurbishing public benches, and installing a new youth shelter. A key focus is improving accessibility in Berinsfield parks by installing play equipment designed for children with Special Educational Needs and Disabilities (SEND), ensuring that all public spaces are safe, inclusive, and welcoming. This project will be delivered by the BGV Team in partnership with BPC. • Drainage of Berinsfield Sports Fields – £110,000 This project involves installing a drainage system on the recreation field. SODC plans to transfer these funds to BPC, allowing them to deliver the project independently. The transfer will be formalised through a funding agreement (subject to SODC formal approval). • MUGA - £200,000 This project seeks to transform the outdated basketball court next to Abbey Sports Centre into a modern, multi-functional facility to better serve the community's needs. SODC is currently negotiating a Lease Agreement with OCC, which must be finalised before the project delivery can begin.; 2025-06-25: Our National Graduate Officer who joined the Communities team is currently focusing on this work to help us to sustain and complete priorities in the Community Delivery Plan.
27 | Openness and accountability | Communications | In progress | M | As an underpinning service / activity, all the above projects will be incorporated into a comms strategy to ensure active and regular communication with the local community. To work with local volunteers to support the continuation and creation of the Village Voice, its production and distribution. To align the BGV virtual newsletter to compliment this offering. | SODC - BGV | 1500 | 450 | 1125 | SODC - BGV | On going, noted that our South website needs to be updated more regularly. Newsletter due out end of November, following upgrade to software system. | South website currently being reviewed and updated for the Berinsfield Garden Village landing pages. |  |  | South website has been reviewed and updated for the Berinsfield Garden Village landing pages and will go live in early April. Website content and structure to be kept under review with input and feedback from the Berinsfield GV Steering Group. Newsletter ready to be circulated in early April and communication and promotion planned including to the Steering Group and partners. | Newsletter has been circulated and Service Manager has been asked to review and approve the planned website changes. Once approval has been received. the changes will be implemented. The Steering Group is being kept updated on the communications developments at each meeting. | Village Voice continues. Updates to the SODC landing pages completed. New issue of the e-newsletter circulated for publication. Further promotion of the newsletter to take place and consideration to be given on the adoption/hosting of an accessible interactive Berinsfield map. |  | 2024-09-01: A thorough update to the Berinsfield Garden Village landing pages on the SODC website was completed. Regular updates will be posted on this page. Project updates will also be included in the Village Voice with the latest article being distributed in the October 2024 edition.; 2024-10-01: Wendy attended Village Voice newsletter meeting and we submitted a project update for the Oct/Nov edition.; 2024-12-01: The Garden Communities programme updates are provided in the bi-monthly editions of the Berinsfield Village Voice.; 2025-01-01: Village Voice article for Garden Community will be circulated at the beginning of February,; 2025-02-01: The Garden Communities programme updates are provided in the bi-monthly editions of the Berinsfield Village Voice. The team also provided a comprehensive update on all BGV projects before monthly BPC meetings which takes place on the first Monday of each month.; 2025-03-01: The Garden Communities programme updates are provided in the bi-monthly editions of the Berinsfield Village Voice. The team also provided a comprehensive update on all BGV projects before monthly BPC meetings which takes place on the first Monday of each month. The PC have developed a social media page and post Garden Village Project updates. The CDO also has a What's App group of volunteers for the Spinney Forest School workforce.; 2025-06-25: Berinsfield Garden Village programme updates were published in the latest edition of the Village Voice in June 2025. We will also add events to the Berinsfield Community Calendar.
[6 empty] | BALANCE | 603531 | 392317.58 | 236435.92 | SODC - BGV
UKSPF Capital Schemes | [11 empty] | January 2024 Update | February Update | March Update |  |  |  |  | 2024-08-01: 2024-08-01; 2024-09-01: 2024-09-01; 2024-12-01: 2024-12-01; 2025-01-01: 2025-01-01; 2025-02-01: 2025-02-01; 2025-03-01: 2025-03-01; 2025-06-25: 2025-06-25
28 | Homes and infrastructure that meet local needs | Skatepark and pump track | Completed | H | In 2023, the Garden Communities team successfully obtained an allocation of UK Shared Prosperity Funding. The team will continue to progress and deliver on the outcomes set out under our proposals for E2 and E3 funding following engagement with the Steering Group and stakeholders in 2023. Ensure our workplans deliver on our commitments that were approved by South and Vale as part of the UKSPF Investment Plan developed by the Economic Development team. | SODC - BGV | 141460 | 141460 | 0 | SODC - UKSPF SODC - CIL |  | Work is underway to plan for the construction of a new Multi Use Games Area (MUGA) within Berinsfield (subject to approval from land owners) to complement the recreational facilities, improve use of open spaces and community facilities. Site options are currently being explore and engagement on potential uses will be completed with the community. |  | MUGA conversations taking place with OCC - but may not be viable because of land ownership and will not align with UKSPF timings. HK has met with the PC and have shared some other options for projects that could be applicable. Other projects may include: BMX park - pump track Improvement to Park/Skate Park Flood alievation - linking to SUDS/Rain garden/Spinney? Seating for young people, basket ball hoop etc Hen exploring options for projects and will share with NW/JB to get steer. Do we need further engagement with the community? Follow up meeting to be held with JB/TO ahead of engaging with RB. To touch base with Eco Development team to understand if projects are eligible | Seating: creating a voting options sheet for BGV steering group to confirm bench designs and locations. Planting: locations have been presented at BGV steering group 10 April. Will proceed with transfer of funds. Pocket Parks: locations and plans presented at BGV steering group, need to transfer funds to Soha, this will be via a funding award letter / waiting for Church to confirm quote on benches and planters with ACE, Sarah is back from Kenya and hopefully project will proceed, met with BPC grounds maintenance to discuss garden path to make it accessible, waiting for their quote / Abbey Woods Spinney GW 2 form should be completed this week, ready for SMT next week, will arrange working party for end of April, still waiting to meet with pre primary school contacts, have requested surveys to be completed, need to arrange survey payment via PO's, also waiting for OCC to confirm final survey cost / Final meeting on MUGA replacement project is taking place Monday 15 April, once confirmed, will start draft ICMD, Funding Agreement and requesting for this decision to be placed on Cabinet Workplan. | Skatepark / Pump track: waiting to hear back from BPC, procurement docs almost done, DA with Andrew, 24 May final date of decision to agree transfer of funds, BPC will lead on tendering process this week, need to call one more company before final ITT, DA for planting and seats almost done, need to check it's okay to procure all seats on behalf of all land owners, need to do seat survey, samples arrived, need to do Funding Agreement Letters for Soha / Church / BPC regarding pocket parks and planting funds Planting on SODC land has been confirmed, need to sort out internal transfer to Tree Officer budget code, GW 2 form for Spinney is with Nicole / GW 2 form for Planting/Pocket | Following site options being explored, we now have to move forward with an alternative project to substitute the MUGA due to land ownership and leasing agreements that will delay the commencement of the project and not align to the UKSPF spending timeline. However, the regeneration of the area is still important and there will be plenty of other external funding opportunities to advance this. A DA to transfer UK SPF to BPC for these projects was approved, and added to the Cabinet Work plan for 28 days and 7 day call in period. Invitation to Tender for these projects went out to four contractors. Monday 3 June BPC delegated authority to their Open Spaces Committee to oversee the work for the skatepark and pump track projects. This committee met Monday 10 June and chose to offer the skatepark work to Bendcrete and the pump track work to C & K Contractors. First site meetings took place Monday 17 June. Contracts are currently being finalised. Initial payment of UK SPF will be paid in the next two weeks. A draft Funding Agreement is with BPC for review before final signatures and payment of remaining Funds. An ICMD requesting permission to transfer £10,000 CIL to support these project is with Legal for comment. Without this ICMD signed of, final funds cannot be paid. |  | 2024-08-01: Procured Planning Consultants, waiting for application technical studies to be completed and for contractor contracts to be signed; 2024-09-01: Technical studies and surveys to inform the planning application for the skatepark and BMX pump track projects is currently underway. Submission of a planning application is due at the end of October 2024. The funding agreement between SODC and Berinsfield Parish Council was complete and a stage 2 payment to transfer the funds is in process.; 2024-12-01: The planning application for the extension to the skatepark and new provision of a BMX pump track was submitted in December 2024 under reference P24/S3616/FUL. The public consultation on the application will close on 5 January 2025. Application is due to be determined by 28 January 2025.; 2025-01-01: The planning application for the extension to the skatepark and new provision of a BMX pump track was submitted in December 2024 under reference P24/S3616/FUL. The public consultation on the application will close on 5 January 2025. Application is due to be determined by 28 January 2025. Extension provided to allow team to complete a Habitat Management Report to address any condition that may come with planning approval.; 2025-02-01: Planning permission was granted on 14 February. As part of the Biodiversity Net Gain requirements, we are required to plant eight trees for the project to proceed. However, since the Parish Council had already planned tree planting in the nearby area, only four additional trees are needed. Over the next month, priority will be given to completing this tree planting and finalizing construction start dates. Both contractors have held pre-construction meetings with BPC, and the remaining UK SPF funds have been transferred to BPC.; 2025-03-01: Planning permission was granted on 14 February. As part of the Biodiversity Net Gain requirements, we are required to plant eight trees for the project to proceed. However, since the Parish Council had already planned tree planting in the nearby area, only four additional trees are needed. Over the next month, priority will be given to completing this tree planting and finalising construction start dates. Both contractors have held pre-construction meetings with BPC, and the remaining UK SPF funds have been transferred to BPC. Communication with residents on the site activity will be completed, with construction underway with practical completion between mid to end of May, weather dependent.; 2025-05-25: The skatepark extension and improvents project was completed and re-opened on 16 May. A launch event will go ahead on the 13 July with demonstrations including safety awareness. The pump track is due to be completed on the 6 June.; 2025-06-25: The Skatepark and Pump Track construction is now complete and open to the public. Both facilities are proving popular with residents. A launch event will go ahead on the 12 July with demonstrations including safety awareness.
29 | Homes and infrastructure that meet local needs | Pocket parks | Completed | H | In 2023, the Garden Communities team successfully obtained an allocation of UK Shared Prosperity Funding. The team will continue to progress and deliver on the outcomes set out under our proposals for E2 and E3 funding following engagement with the Steering Group and stakeholders in 2023. Ensure our workplans deliver on our commitments that were approved by South and Vale as part of the UKSPF Investment Plan developed by the Economic Development team. | SODC/ Soha / BGV / Church / BCA/ Berin Centre/ BPC | 41065 | 41065 | 0 | SODC - UKSPF SODC - CIL | [6 empty] | A DA requesting the transfer of UK SPF and an ICMD requesting CIL funds to support the creation of pocket parks are currently delayed with Legal, impacting the delivery timeline of these projects. Soha has begun community consultations for their two pocket parks. We have received the tree and ecological reports for the Abbey Woods Spinney pocket park/forest school and will be contracting Leaves of Green for the landscaping design. BPC will procure construction services for the works using UK SPF and CIL funds. Oxfordshire CAB is involved with the church pocket park/community garden and will have a part-time post to support its development and management for the next two years, the church will be contracting Oxford Direct Services and ACE to do the work once they receive the funds. |  | 2024-09-01: All funding was awarded and administered to all organisations SODC are working in partnership with to delivery the pocket park outcomes. Partner organisations include Berinsfield Parish Council, St Mary and St Berin Church, the Berin Centre, BCA, SOHA and CAG. Phase one of the Church Community Garden was completed in early August and a new pathway was installed. We've partnered with The Berin Centre and CAG Oxfordshire, who have hired a new Community Garden Coordinator to help advance the community garden. The coordinator will oversee the installation of planters, a bench, and a toolshed over the coming months. Berinsfield Parish Council has agreed to move forward with a volunteer build approach to implement the groundwork for the Abbey Woods Spinney enhancement and forthcoming Forest School. Over 20 residents, along other community organisations have offered to participate. Leaves of Green will be contracted to coordinate the materials, equipment, and volunteers on the agreed day.; 2024-12-01: Construction of all pocket parks are currently underway at all locations/land ownership outlined below, which are scheduled to be completed by March 2025: - St Mary and St Berin Church - Berinsfield Community Association - SOHA (Pétanque Court/Chiltern Close); 2025-01-01: Construction of all pocket parks are currently underway at all locations/land ownership outlined below, which are scheduled to be completed by March 2025: - St Mary and St Berin Church - Berinsfield Community Association - SOHA (Pétanque Court/Chiltern Close); 2025-02-01: Construction of all pocket parks are currently underway at all locations/land ownership outlined below, which are scheduled to be completed by March 2025: - St Mary and St Berin Church - Berinsfield Community Association - SOHA: due to staffing issues, a decision was made to claw back some funds for the second pocket park Soha was responsible for building, and re-allocated to other projects. The pétanque court has now been completed.; 2025-03-01: Construction of all pocket parks or green infrastructure improvements, including wayfinding signage are currently underway at all locations/land ownership outlined below, which are scheduled to be completed by March 2025: - St Mary and St Berin Church - Berinsfield Community Association - SOHA - Berinsfield Voluntary Day Centre - Berry Youth Centre - Berinsfield Early Years Pre School - Abbey Woods Academy - Abbey Woods Spinney; 2025-05-25: This is now completed.; 2025-06-25: This is now completed.
30 | Homes and infrastructure that meet local needs | Planting | Completed | H | In 2023, the Garden Communities team successfully obtained an allocation of UK Shared Prosperity Funding. The team will continue to progress and deliver on the outcomes set out under our proposals for E2 and E3 funding following engagement with the Steering Group and stakeholders in 2023. Ensure our workplans deliver on our commitments that were approved by South and Vale as part of the UKSPF Investment Plan developed by the Economic Development team. | SODC - Soha / BGV / Church / BCA | 9000 | 8600 | 400 | SODC - UKSPF | [6 empty] | A DA requesting the transfer of UK SPF for additional planting in Berinsfield is currently delayed with Legal, impacting the delivery timeline. BPC will receive funds for 6 new trees and wildflower seeds to use on their land. Soha is receiving additional funds for trees, plants and wildflower seeds on their land. SODC Tree Officer will receive funds for 26 new trees on our land in Berinsfield. The Church will receive funds toward planters for their community garden and Berinsfield Community Association will create a pocket park behind their building, which is currently overgrown and not utilized by members and guests. |  | 2024-09-01: As per update outlined in project 29, funding to advance pocket park projects was awarded and administered to all organisations. As part of this wider scheme, funding will be used to plant new species within each area. For example, Soha is receiving additional funds for trees, plants and wildflower seeds on their land. Further tree planting on SODC owned land in Berinsfield will commence in January/February 2025.; 2024-12-01: We will be planting a total of 33 trees in Berinsfield by February 2025 on SODC and other land owned by partners.; 2025-01-01: We will be planting a total of 33 trees in Berinsfield by February 2025 on SODC and other land owned by partners.; 2025-02-01: Two Scots Pines were planted at Abbey Woods Spinney, 36 new trees were planted on SODC land in Berinsfield, and Berinsfield Parish Council is about to plant six new trees on their land. As part of BNG for the skatepark and pump track construction, a further four trees will be planted on BPC land.; 2025-03-01: Two Scots Pines were planted at Abbey Woods Spinney, 36 new trees were planted on SODC/OCC land in Berinsfield, and Berinsfield Parish Council is about to plant six new trees on their land. As part of BNG for the skatepark and pump track construction, a further four trees will be planted on BPC land. Stage 2 of Abbey Woods Spinney improvements is in progress.; 2025-05-25: This is now completed.; 2025-06-25: This is now completed.
31 | Homes and infrastructure that meet local needs | Seating | Completed | H | In 2023, the Garden Communities team successfully obtained an allocation of UK Shared Prosperity Funding. The team will continue to progress and deliver on the outcomes set out under our proposals for E2 and E3 funding following engagement with the Steering Group and stakeholders in 2023. Ensure our workplans deliver on our commitments that were approved by South and Vale as part of the UKSPF Investment Plan developed by the Economic Development team. | SODC - Soha / BGV / Church / BCA | 7000 | 6810 | 190 | SODC - UKSPF | [6 empty] | To assist in developing a design guide for Berinsfield, we have distributed a survey to stakeholders seeking feedback on the location, style, colour, and material for new benches. The survey results will be presented at the October Steering Group meeting, after which we will proceed with the procurement and installation of the new benches. |  | 2024-09-01: Locations are identified for new seating, following initial feedback from the community at the Summer Fete. This element of the project and installation will commence early 2025.; 2024-12-01: Additional seating for the recreation field was ordered for manufacturing and will be installed by the end of March 2025.; 2025-01-01: Additional seating for the recreation field was ordered for manufacturing and will be installed by the end of March 2025.; 2025-02-01: Additional seating for the recreation field was ordered for manufacturing and will be installed by the end of March 2025.; 2025-03-01: Additional seating for the recreation field was installed.; 2025-05-25: This is now completed.; 2025-06-25: This is now completed.
[6 empty] | BALANCE | 198525 | 197935 | 590 | SODC - UKSPF SODC - CIL
CIL Capital Schemes | [11 empty] | January 2024 Update | February Update | March Update |  |  |  |  | 2024-08-01: 2024-08-01; 2024-09-01: 2024-09-01; 2024-12-01: 2024-12-01; 2025-01-01: 2025-01-01; 2025-02-01: 2025-02-01; 2025-03-01: 2025-03-01; 2025-05-25: 2025-05-01; 2025-06-25: 2025-06-25
32 | Homes and infrastructure that meet local needs | Berinsfield signage and amenities upgrade project | In progress | H | This project seeks to revitalise the village by upgrading its infrastructure and enhancing its appearance. Key initiatives include replacing outdated street signs, bins, and welcome signs, refurbishing public benches, and installing a new youth shelter. A key focus is improving accessibility in Berinsfield parks by installing play equipment designed for children with Special Educational Needs and Disabilities (SEND), ensuring that all public spaces are safe, inclusive, and welcoming. | SODC | 92413 |  |  | CIL |  | Work is underway to plan for the construction of a new Multi Use Games Area (MUGA) within Berinsfield (subject to approval from land owners) to complement the recreational facilities, improve use of open spaces and community facilities. Site options are currently being explore and engagement on potential uses will be completed with the community. |  | MUGA conversations taking place with OCC - but may not be viable because of land ownership and will not align with UKSPF timings. HK has met with the PC and have shared some other options for projects that could be applicable. Other projects may include: BMX park - pump track Improvement to Park/Skate Park Flood alievation - linking to SUDS/Rain garden/Spinney? Seating for young people, basket ball hoop etc Hen exploring options for projects and will share with NW/JB to get steer. Do we need further engagement with the community? Follow up meeting to be held with JB/TO ahead of engaging with RB. To touch base with Eco Development team to understand if projects are eligible | Seating: creating a voting options sheet for BGV steering group to confirm bench designs and locations. Planting: locations have been presented at BGV steering group 10 April. Will proceed with transfer of funds. Pocket Parks: locations and plans presented at BGV steering group, need to transfer funds to Soha, this will be via a funding award letter / waiting for Church to confirm quote on benches and planters with ACE, Sarah is back from Kenya and hopefully project will proceed, met with BPC grounds maintenance to discuss garden path to make it accessible, waiting for their quote / Abbey Woods Spinney GW 2 form should be completed this week, ready for SMT next week, will arrange working party for end of April, still waiting to meet with pre primary school contacts, have requested surveys to be completed, need to arrange survey payment via PO's, also waiting for OCC to confirm final survey cost / Final meeting on MUGA replacement project is taking place Monday 15 April, once confirmed, will start draft ICMD, Funding Agreement and requesting for this decision to be placed on Cabinet Workplan. | Skatepark / Pump track: waiting to hear back from BPC, procurement docs almost done, DA with Andrew, 24 May final date of decision to agree transfer of funds, BPC will lead on tendering process this week, need to call one more company before final ITT, DA for planting and seats almost done, need to check it's okay to procure all seats on behalf of all land owners, need to do seat survey, samples arrived, need to do Funding Agreement Letters for Soha / Church / BPC regarding pocket parks and planting funds Planting on SODC land has been confirmed, need to sort out internal transfer to Tree Officer budget code, GW 2 form for Spinney is with Nicole / GW 2 form for Planting/Pocket | Following site options being explored, we now have to move forward with an alternative project to substitute the MUGA due to land ownership and leasing agreements that will delay the commencement of the project and not align to the UKSPF spending timeline. However, the regeneration of the area is still important and there will be plenty of other external funding opportunities to advance this. A DA to transfer UK SPF to BPC for these projects was approved, and added to the Cabinet Work plan for 28 days and 7 day call in period. Invitation to Tender for these projects went out to four contractors. Monday 3 June BPC delegated authority to their Open Spaces Committee to oversee the work for the skatepark and pump track projects. This committee met Monday 10 June and chose to offer the skatepark work to Bendcrete and the pump track work to C & K Contractors. First site meetings took place Monday 17 June. Contracts are currently being finalised. Initial payment of UK SPF will be paid in the next two weeks. A draft Funding Agreement is with BPC for review before final signatures and payment of remaining Funds. An ICMD requesting permission to transfer £10,000 CIL to support these project is with Legal for comment. Without this ICMD signed of, final funds cannot be paid. |  | 2024-08-01: Procured Planning Consultants, waiting for application technical studies to be completed and for contractor contracts to be signed; 2024-09-01: Technical studies and surveys to inform the planning application for the skatepark and BMX pump track projects is currently underway. Submission of a planning application is due at the end of October 2024. The funding agreement between SODC and Berinsfield Parish Council was complete and a stage 2 payment to transfer the funds is in process.; 2024-12-01: Project not yet started.; 2025-01-01: Project not yet started.; 2025-02-01: Informed of successful application and shared the news with BPC - started internal governance process for funds to be transferred from transitional budget to capital programmes budget.; 2025-03-01: SODC formally approved funding for project in February 2025. Internal governance process for funds to be bought forward to the capital programme is underway. SODC will lead on this project, in close co-ordination with OCC who were also successful in securing further funds.; 2025-05-25: Project scoping including estimates obtained to understand budget and delivery capabilities more. Working alonside OCC who have a further £30,000 for Wayfinding and Healthy Placeshaping in Berinsfifeld.; 2025-06-25: Project scoping is underway to outline a proposal for the project including estimates obtained to understand budget and delivery capabilities more. Offices are currently working alonside OCC who have a further £30,000 for Wayfinding and Healthy Placeshaping in Berinsfield.
33 | Homes and infrastructure that meet local needs | Drainage of Berinsfield Sports Fields | In progress | H | This project involves installing a drainage system on the recreation field. | BPC/SODC | 110000 |  |  | CIL | [6 empty] | A DA requesting the transfer of UK SPF and an ICMD requesting CIL funds to support the creation of pocket parks are currently delayed with Legal, impacting the delivery timeline of these projects. Soha has begun community consultations for their two pocket parks. We have received the tree and ecological reports for the Abbey Woods Spinney pocket park/forest school and will be contracting Leaves of Green for the landscaping design. BPC will procure construction services for the works using UK SPF and CIL funds. Oxfordshire CAB is involved with the church pocket park/community garden and will have a part-time post to support its development and management for the next two years, the church will be contracting Oxford Direct Services and ACE to do the work once they receive the funds. |  | 2024-09-01: All funding was awarded and administered to all organisations SODC are working in partnership with to delivery the pocket park outcomes. Partner organisations include Berinsfield Parish Council, St Mary and St Berin Church, the Berin Centre, BCA, SOHA and CAG. Phase one of the Church Community Garden was completed in early August and a new pathway was installed. We've partnered with The Berin Centre and CAG Oxfordshire, who have hired a new Community Garden Coordinator to help advance the community garden. The coordinator will oversee the installation of planters, a bench, and a toolshed over the coming months. Berinsfield Parish Council has agreed to move forward with a volunteer build approach to implement the groundwork for the Abbey Woods Spinney enhancement and forthcoming Forest School. Over 20 residents, along other community organisations have offered to participate. Leaves of Green will be contracted to coordinate the materials, equipment, and volunteers on the agreed day.; 2024-12-01: Project not yet started.; 2025-01-01: Project not yet started.; 2025-02-01: Informed of successful application and shared the news with BPC - started internal governance process for funds to be transferred from transitional budget to capital programmes budget and to seek permission to transfer funds to BPC who will lead on this project. Legal will be instructed to draw up a Funding Agreement for funds to be transferred to BPC.; 2025-03-01: SODC formally approved funding for project in February 2025. Internal governance process for funds to be bought forward to the capital programme and transferred to the Parish Council is underway. Berinsfield Parish Council provisionally agreed to lead on project. Legal will be instructed to draw up a Funding Agreement.; 2025-05-25: Legal agreement currently being drafted for the Parish Coucil to accept the funding to progress this project.; 2025-06-25: A legal agreement currently being drafted for the Parish Coucil to accept the funding to progress this project.
34 | Homes and infrastructure that meet local needs | MUGA | In progress | H | This project seeks to transform the outdated basketball court next to Abbey Sports Centre into a modern, multi-functional facility to better serve the community's needs. | SODC/OCC | 200000 |  |  | CIL | [6 empty] | A DA requesting the transfer of UK SPF for additional planting in Berinsfield is currently delayed with Legal, impacting the delivery timeline. BPC will receive funds for 6 new trees and wildflower seeds to use on their land. Soha is receiving additional funds for trees, plants and wildflower seeds on their land. SODC Tree Officer will receive funds for 26 new trees on our land in Berinsfield. The Church will receive funds toward planters for their community garden and Berinsfield Community Association will create a pocket park behind their building, which is currently overgrown and not utilized by members and guests. |  | 2024-09-01: As per update outlined in project 29, funding to advance pocket park projects was awarded and administered to all organisations. As part of this wider scheme, funding will be used to plant new species within each area. For example, Soha is receiving additional funds for trees, plants and wildflower seeds on their land. Further tree planting on SODC owned land in Berinsfield will commence in January/February 2025.; 2024-12-01: Project not yet started.; 2025-01-01: Project not yet started.; 2025-02-01: Informed of successful application and shared the news with BPC - started internal governance process for funds to be transferred from transitional budget to capital programmes budget. SODC is currently negotiating a Lease Agreement with OCC, which must be finalised before the project delivery can begin. This has been raised as a risk to the delivery of this project especially as the lease agreement may only be in place April 2026.; 2025-03-01: SODC formally approved funding for project in February 2025. Internal governance process for funds to be bought forward to the capital programme is underway. SODC will lead on this project.; 2025-05-25: Negotiations are currently underway between OCC and SODC on the JUA of the site, to support the project being bought forward.; 2025-06-25: OCC and SODC have progressed discussions around the Joint Use Agreement of Abbey Sports Centre, in light of Local Govenment Reorganisation. This means overdue works to the sports centre flooring and MUGA can now be undertaken. Initial concepts design for the MUGA will be progressed by our Leisure Development team.
[6 empty] | BALANCE | 402413 | 0 | 402413 | SODC - CIL

## Timeline
Programme Manager (PgM): | Nicola Wyer | [9 empty] | 2025-01-25 | [29 empty] | 2025-02-24 | [30 empty] | 2025-03-27 | [30 empty] | 2025-04-27 | [29 empty] | 2025-05-27 | [30 empty] | 2025-07-13 | [29 empty] | 2025-08-12 | [30 empty] | 2025-09-12 | [30 empty] | 2025-10-12 | [27 empty] | 2025-11-12 | [30 empty] | 2025-12-13 | [29 empty] | 2026-01-10 | [30 empty] | 2026-02-10 | [29 empty] | 2026-03-12 | [30 empty] | 2026-04-12 | [30 empty] | 2026-05-12 | [29 empty] | 2026-06-12 | [30 empty] | 2026-07-13 | [29 empty] | 2026-08-12 | [30 empty] | 2026-09-12 | [30 empty] | 2026-10-12 | [27 empty] | 2026-11-12 | [30 empty] | 2026-12-13 | [29 empty] | 2027-01-10 | [30 empty] | 2027-02-10 | [29 empty] | 2027-03-12 | [30 empty] | 2027-03-28
Start Date: | 2025-01-01 |  |  | 4 |  | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12 | [6 empty] | Week 13 | [6 empty] | Week 14 | [6 empty] | Week 15 | [6 empty] | Week 16 | [6 empty] | Week 17 | [6 empty] | Week 18 | [6 empty] | Week 19 | [6 empty] | Week 20 | [6 empty] | Week 21 | [6 empty] | Week 22 | [6 empty] | Week 23 | [6 empty] | Week 24 | [6 empty] | Week 25 | [6 empty] | Week 26 | [6 empty] | Week 27 | [6 empty] | Week 28 | [6 empty] | Week 29 | [6 empty] | Week 30 | [6 empty] | Week 31 | [6 empty] | Week 32 | [6 empty] | Week 33 | [6 empty] | Week 34 | [6 empty] | Week 35 | [6 empty] | Week 36 | [6 empty] | Week 37 | [6 empty] | Week 38 | [6 empty] | Week 39 | [6 empty] | Week 40 | [6 empty] | Week 41 | [6 empty] | Week 42 | [6 empty] | Week 43 | [6 empty] | Week 44 | [6 empty] | Week 45 | [6 empty] | Week 46 | [6 empty] | Week 47 | [6 empty] | Week 48 | [6 empty] | Week 49 | [6 empty] | Week 50 | [6 empty] | Week 51 | [6 empty] | Week 52 | [6 empty] | Week 53 | [6 empty] | Week 54 | [6 empty] | Week 55 | [6 empty] | Week 56 | [6 empty] | Week 57 | [6 empty] | Week 58 | [6 empty] | Week 59 | [6 empty] | Week 60 | [6 empty] | Week 61 | [6 empty] | Week 62 | [6 empty] | Week 63 | [6 empty] | Week 64 | [6 empty] | Week 65 | [6 empty] | Week 66 | [6 empty] | Week 67 | [6 empty] | Week 68 | [6 empty] | Week 69 | [6 empty] | Week 70 | [6 empty] | Week 71 | [6 empty] | Week 72 | [6 empty] | Week 73 | [6 empty] | Week 74 | [6 empty] | Week 75 | [6 empty] | Week 76 | [6 empty] | Week 77 | [6 empty] | Week 78 | [6 empty] | Week 79 | [6 empty] | Week 80 | [6 empty] | Week 81 | [6 empty] | Week 82 | [6 empty] | Week 83 | [6 empty] | Week 84 | [6 empty] | Week 85 | [6 empty] | Week 86 | [6 empty] | Week 87 | [6 empty] | Week 88 | [6 empty] | Week 89 | [6 empty] | Week 90 | [6 empty] | Week 91 | [6 empty] | Week 92 | [6 empty] | Week 93 | [6 empty] | Week 94 | [6 empty] | Week 95 | [6 empty] | Week 96 | [6 empty] | Week 97 | [6 empty] | Week 98 | [6 empty] | Week 99 | [6 empty] | Week 100 | [6 empty] | Week 101 | [6 empty] | Week 102 | [6 empty] | Week 103 | [6 empty] | Week 104 | [6 empty] | Week 105 | [6 empty] | Week 106 | [6 empty] | Week 107 | [6 empty] | Week 108 | [6 empty] | Week 109 | [6 empty] | Week 110 | [6 empty] | Week 111 | [6 empty] | Week 112 | [6 empty] | Week 113 | [6 empty] | Week 114 | [6 empty] | Week 115 | [6 empty] | Week 116 | [6 empty] | Week 117 | [6 empty] | Week 118 | [6 empty] | Week 119
 | time axis 2025-01-20 to 2027-04-11
 | time axis 2025-01-20 to 2027-04-11
PROJECT & TASK | BGV LEAD | START | END | % DONE | WORK DAYS | 2025-01-20: 2025-01-20; 2025-01-27: 2025-01-27; 2025-02-03: 2025-02-03; 2025-02-10: 2025-02-10; 2025-02-17: 2025-02-17; 2025-02-24: 2025-02-24; 2025-03-03: 2025-03-03; 2025-03-10: 2025-03-10; 2025-03-17: 2025-03-17; 2025-03-24: 2025-03-24; 2025-03-31: 2025-03-31; 2025-04-07: 2025-04-07; 2025-04-14: 2025-04-14; 2025-04-21: 2025-04-21; 2025-04-28: 2025-04-28; 2025-05-05: 2025-05-05; 2025-05-12: 2025-05-12; 2025-05-19: 2025-05-19; 2025-05-26: 2025-05-26; 2025-06-02: 2025-06-02; 2025-06-09: 2025-06-09; 2025-06-16: 2025-06-16; 2025-06-23: 2025-06-23; 2025-06-30: 2025-06-30; 2025-07-07: 2025-07-07; 2025-07-14: 2025-07-14; 2025-07-21: 2025-07-21; 2025-07-28: 2025-07-28; 2025-08-04: 2025-08-04; 2025-08-11: 2025-08-11; 2025-08-18: 2025-08-18; 2025-08-25: 2025-08-25; 2025-09-01: 2025-09-01; 2025-09-08: 2025-09-08; 2025-09-15: 2025-09-15; 2025-09-22: 2025-09-22; 2025-09-29: 2025-09-29; 2025-10-06: 2025-10-06; 2025-10-13: 2025-10-13; 2025-10-20: 2025-10-20; 2025-10-27: 2025-10-27; 2025-11-03: 2025-11-03; 2025-11-10: 2025-11-10; 2025-11-17: 2025-11-17; 2025-11-24: 2025-11-24; 2025-12-01: 2025-12-01; 2025-12-08: 2025-12-08; 2025-12-15: 2025-12-15; 2025-12-22: 2025-12-22; 2025-12-29: 2025-12-29; 2026-01-05: 2026-01-05; 2026-01-12: 2026-01-12; 2026-01-19: 2026-01-19; 2026-01-26: 2026-01-26; 2026-02-02: 2026-02-02; 2026-02-09: 2026-02-09; 2026-02-16: 2026-02-16; 2026-02-23: 2026-02-23; 2026-03-02: 2026-03-02; 2026-03-09: 2026-03-09; 2026-03-16: 2026-03-16; 2026-03-23: 2026-03-23; 2026-03-30: 2026-03-30; 2026-04-06: 2026-04-06; 2026-04-13: 2026-04-13; 2026-04-20: 2026-04-20; 2026-04-27: 2026-04-27; 2026-05-04: 2026-05-04; 2026-05-11: 2026-05-11; 2026-05-18: 2026-05-18; 2026-05-25: 2026-05-25; 2026-06-01: 2026-06-01; 2026-06-08: 2026-06-08; 2026-06-15: 2026-06-15; 2026-06-22: 2026-06-22; 2026-06-29: 2026-06-29; 2026-07-06: 2026-07-06; 2026-07-13: 2026-07-13; 2026-07-20: 2026-07-20; 2026-07-27: 2026-07-27; 2026-08-03: 2026-08-03; 2026-08-10: 2026-08-10; 2026-08-17: 2026-08-17; 2026-08-24: 2026-08-24; 2026-08-31: 2026-08-31; 2026-09-07: 2026-09-07; 2026-09-14: 2026-09-14; 2026-09-21: 2026-09-21; 2026-09-28: 2026-09-28; 2026-10-05: 2026-10-05; 2026-10-12: 2026-10-12; 2026-10-19: 2026-10-19; 2026-10-26: 2026-10-26; 2026-11-02: 2026-11-02; 2026-11-09: 2026-11-09; 2026-11-16: 2026-11-16; 2026-11-23: 2026-11-23; 2026-11-30: 2026-11-30; 2026-12-07: 2026-12-07; 2026-12-14: 2026-12-14; 2026-12-21: 2026-12-21; 2026-12-28: 2026-12-28; 2027-01-04: 2027-01-04; 2027-01-11: 2027-01-11; 2027-01-18: 2027-01-18; 2027-01-25: 2027-01-25; 2027-02-01: 2027-02-01; 2027-02-08: 2027-02-08; 2027-02-15: 2027-02-15; 2027-02-22: 2027-02-22; 2027-03-01: 2027-03-01; 2027-03-08: 2027-03-08; 2027-03-15: 2027-03-15; 2027-03-22: 2027-03-22; 2027-03-29: 2027-03-29; 2027-04-05: 2027-04-05
1-4 HIF | OCC | 2026-03-30 | 2028-03-31 |  | 525
Science Bridge | OCC | 2026-03-30 | 2028-03-31 | 0%
A4130 improvements | OCC | 2026-03-30 | 2028-03-31 | 0% | 525
Clifton Hampden bypass | OCC | 2026-03-30 | 2028-03-31 | 0% | 525
Culham Thames crossing | OCC | 2026-03-30 | 2028-03-31 | 0% | 525
5. Didcot Central Corridor (OCC) | OCC | 2023-06-30 | 2024-12-20 |  | 386
Draft Stage 1 Options Appraisal Report | OCC | 2023-06-30 | 2024-12-20 | 75%
6. NPR3 (OCC) | OCC | 2025-01-31 | 2025-08-01 |  | 131
Planningapplication | OCC | 2025-01-31 | 2025-08-01 | 5%
Construction | OCC | 2025-09-01 | 2026-12-20 | 0%
7. Gateway masterplan | Homes England | 2022-02-04 | 2025-02-19 |  | 794
Planning application P22/S4091 | Homes England | 2022-02-04 | 2025-02-19 | 99%
8. Gateway Council Offices | SAV | 2025-01-31 | 2025-03-12 |  | 29
Planning application P23/S2621/FUL | SAV | 2025-01-31 | 2025-03-12 | 5%
Construction (subject to LGR) | SAV | 2026-01-05 | 2028-12-20 | 0%
1. LAND & DELIVERY AGMT |  | 2025-01-01 | 2026-03-30 |  | 324
ADD LINK TO FOLDER
Negotiations - S123 | Property | 2025-01-27 | 2025-10-07 | 25% | 182
Negoitations - S203 | EW/AS | 2025-01-27 | 2025-10-07 | 25%
Negotiations - S106 | EW/AS/NW | 2025-03-10 | 2026-03-30 | 25% | 276
ToR | EW | 2025-01-01 | 2026-03-30 | 0% | 324
13. Science Vale Area Travel Plan (OCC) | SAV | 0 | 0 |  | -
Planning application P23/S2621/FUL | SAV |  |  | 5%
SODC Land Owner decision | EW/AS | 2025-01-02 | 2025-05-31 | 30%
2. Community-led Masterplanning |  | 2024-04-01 | 2025-12-30 |  | 457
ADD LINK TO FOLDER
Ptarmigan Community Planning | CC | 2025-01-02 | 2025-12-30 | 45%
Evidece Gathering | AS/NW | 2024-04-01 | 2025-03-30 | 80%
SODC Regeneration Strategy Drafting | AS/NW | 2025-01-02 | 2025-03-30 | 65%
Focus Groups | AS/NW | 2024-05-01 | 2024-08-30 | 100%
Internal Officer Engagemebnt | AS/NW | 2024-10-01 | 2025-02-28 | 85%
Draft Public Consultation Survey | AS/NW/LC | 2024-11-15 | 2025-01-08 | 100%
Public Consultation | NW/WF | 2025-01-09 | 2025-02-08 | 100%
Data Analysis | LC/NW | 2025-02-09 | 2025-02-28 | 95%
Strategy Refinement | AS/NW | 2025-02-10 | 2025-03-30 | 40%
Draft Cabinet Paper/Consultation | NW | 2025-02-24 | 2025-03-30 | 50%
SMT | AS/NW | 2025-03-05 | 2025-03-06 | 0%
Papers to Executive Support | AS/NW | 2025-03-17 | 2025-03-18 | 0%
Cabinet Briefing | AS/NW/JB/EW | 2025-03-21 | 2025-03-22 | 0%
Cabinet | AS/NW/JB/EW | 2025-04-10 | 2025-04-11 | 0%
17. ENV. & SUSTAINABILITY | CDO / PO / PM | 2024-11-01 | 2026-03-31 |  | 368
Environment & Sust. dashboard
2nd Eco fair | CDO / PO | 2024-11-01 | 2024-11-30 | 100% | 21
Energy Champion training | CDO / PO | 2024-11-01 | 2024-11-30 | 100% | 21
Other activities (Trust Green link?) | PM | 2024-12-02 | 2026-03-31 | 0% | 347
18. MEANWWHILE USES | Abi / CDO / PO | 2024-09-01 | 2026-03-30 |  | 411
Meanwhile uses
Joint Local Plan Examination | AS/NW/JB/EW | 2025-06-01 | 2025-06-30 | 0%
03. Community Facilities |  | 2024-09-01 | 2026-03-30 |  | 411
03. Community Facilities
Oxford Architects Stage 1 Commission | AS/EW/NW | 2024-09-01 | 2024-06-01 | 100%
RIBA Stage 1 - Pozini Architects | CT | 2024-10-01 | 2025-01-30 | 100%
RIBA Stage 1-4 | NW/AS | 2025-04-01 | 2026-03-30 | 0% | 260
|  |  |  | 0% | -
|  |  |  | 0% | -
07. Affordable Homes |  | 2024-06-01 | 2025-03-31 |  | 216
Link to folder
Procurement | AS | 2024-06-01 | 2024-07-30 | 100% | 42
Options Research Ltd Report Writing | NW | 2024-08-01 | 2025-01-30 | 100% | 131
Data and Policy Analysis | NW | 2024-08-01 | 2024-09-30 | 100% | 43
Plants PO & planting | CC | 2025-02-03 | 2025-03-31 | 0% | 41
Plants PO & planting | CC | 2025-02-03 | 2025-03-31 | 0% | 41
Transfer budget balance to Berinsfield | CC | 2025-02-03 | 2025-03-31 | 0% | 41
20. DIDCOT LEIS & REC STRATEGY | PgM | 2024-07-01 | 2025-08-29 |  | 305
Extract from district-wide strategies | PgM |  |  | 100% | -
21. AC. & HEALTHY | PM / CDO | 2024-07-01 | 2027-03-31 |  | 718
Activ.Comms & Healthy Didcot dashboard
PMP &PROC01 Insight Rept. | PM | 2024-07-01 | 2024-07-31 | 100% | 23
Insight Report and Action Plan | PM | 2024-10-01 | 2025-03-31 | 70% | 130
ICMD for Action Plan | PM | 2025-04-01 | 2025-04-30 | 0% | 22
Seeking grants for action plan implementation | PM / CDO | 2025-05-01 | 2025-08-29 | 0% | 87
Implementation | PM / CDO | 2025-05-01 | 2027-03-31 | 0% | 500
22. D. TOWN CTR & RETAIL STRAT. | Econ.Dev | 2024-07-27 | 2026-03-31 |  | 437
TBC | Econ. Dev |  |  | 100% | -
23. APPRENTICESHIPS, SKILLS… | PgM | 2024-08-01 | 2026-03-31 |  | 434
Monitoring and reporting | PgM |  |  | 100% | -
25. DIGITAL INCLUSION & COWORK. | PgM | 2024-08-01 | 2026-03-31 |  | 434
Monitoring and reporting | PgM |  |  | 100% | -
26. MILTON BIOSCIENCE CENTRE | PgM | 2024-05-31 | 2026-03-31 |  | 478
Monitoring and reporting | PgM |  |  | 100% | -
27. GDN. PARTY LEGACY | PM / CDO* | 2024-07-27 | 2025-06-28 |  | 240
Gdn.Party & legacy dashboard
DGP launch & events | PM / CDO | 2024-07-27 | 2024-08-31 | 0% | 25
S'holder liaise - DGP legacy | PM / CDO | 2024-10-01 | 2024-12-20 | 0% | 59
DGP Charity Org status | TL / PgM | 2025-01-02 | 2025-06-28 | 0% | 127
27. DGT LEGACY | TL / PgM** | 2024-08-01 | 2026-03-31 |  | 434
PMP DGT Stewardship model | TL / PgM | 2024-08-01 | 2024-08-30 | 0% | 22
Procure St'ship business case | TL /PgM | 2024-09-02 | 2024-11-29 | 0% | 65
Stewardship business case | TL / PgM | 2024-12-02 | 2025-03-31 | 0% | 86
Stewardship engagement | tbc | 2024-12-02 | 2025-03-31 | 0% | 86
Council approve stew. model | TL / PgM | 2025-04-01 | 2025-06-27 | 0% | 64
Implementation | TL / PgM | 2025-06-30 | 2026-03-31 | 0% | 197
COMMS & ENGAGEMENT | TL*** | 2024-05-31 | 2026-03-31 |  | 478
Tewkesbury Gd,Town visit | TL | 2024-08-01 | 2024-08-30 | 0% | 22
Healthy Didcot Survey | PM | 2024-07-05 | 2024-08-20 | 0% | 33
Garden Party comms | tbc | 2024-06-03 | 2024-09-13 | 0% | 75
Garden Party survey | PM | 2024-06-27 | 2024-09-30 | 0% | 68
Discuss Land Mgt DTC/OCC | T L/ PgM | 2024-08-02 | 2025-03-31 | 0% | 172
Developer Forum | T L/ PgM | 2024-09-02 | 2024-11-01 | 0% | 45
DGT Newsletter (quarterly) | tbc | 2024-05-31 | 2026-03-31 | 0% | 478
Didcot TC Comms (monthly) | tbc | 2024-06-03 | 2026-03-31 | 0% | 477
DTC Climate Cttee | T L/ PgM | 2024-08-01 | 2024-08-30 | 0% | 22
Didcot 1st catch-up (quarterly) | All | 2024-07-09 | 2026-03-31 | 0% | 451
RESOURCE MANAGEMENT |  | 2024-08-01 | 2026-03-28 |  | 432
6-weeky DC/OCC officer work group
Support OCC projects
Current team contracts end | TL | 2025-01-01 | 2025-03-31 | 0% | 64
CDO contract end | TL | 2025-08-01 | 2025-08-08 | 0% | 6
Budget growth bids | TL / PgM | 2024-08-01 | 2024-08-30 | 0% | 22
Prep budget/resource bid | TL / PgM | 2024-10-01 | 2025-01-31 | 0% | 89
New Homes Eng Bids | TL / PgM | 2024-12-02 | 2024-12-20 | 0% | 15
Homes Eng. Bid returns | TL / PgM | 2025-03-03 | 2025-03-28 | 0% | 20
Council sets '25-26 budgets | TL / PgM | 2025-02-03 | 2025-02-28 | 0% | 20
Prep budget bids | TL / PgM | 2025-10-01 | 2026-01-31 | 0% | 88
New Homes Eng Bids | TL / PgM | 2025-12-02 | 2025-12-20 | 0% | 14
Homes Eng. Bid returns | TL / PgM | 2026-03-03 | 2026-03-28 | 0% | 19
Council sets '26-27 budgets | TL / PgM | 2026-02-03 | 2026-02-28 | 0% | 19
DGT ADVISORY BOARD
DGT Advisory Board (quarterly | All | 2024-06-25 | 2026-03-31 | bar: 2025-03-10; 2025-06-16; 2025-09-15; 2025-12-15; 2026-03-15; 2026-06-15; 2026-09-14
BAU & OTHER PROJECTS
14. Planning app.comment (BAU) | All
15. Planning Policy input (BAU) | All
1-4 HIF1 (OCC) | TL
5. Didcot Central Corridor (OCC) | TL
6. NPR3 (OCC) | TL
7. Gateway (Homes England)
8. Gateway Council Offices
13. Didcot Area Travel Plan (OCC)
18. Meanwhile uses
20. Didcot Leis & Rec Strategy
22. Retail & Town Centre Study
23. Apprenticeships, skills
24. Digital inclusion
25. LDOs
26. Milton Bio Science Centre
10. Didcot LCWIP |  | COMPLETE |  | 100%
11. Sci. Vale Active Travel Network |  | COMPLETE |  | 100%
12. MultiCAV (aut.bus) trials |  | COMPLETE |  | 100%
X. CornerstoneAction Plan
X. 116-120 Broadway
Gdn. Communties Team Leader (TL) | Nicky Wyer
Programme Manager (PgM): | Charlotte Cottingham
Project Manager (PM): | Emma East
Project Officer (PO): | tbc
Community Devel.Officer (CDO) | Wendy Foster
Contractor (Con)
*hand GPs over to Cornerstone
**do GW1 to test water
***Need dedicated Comms Officer